## Dashboard
Vardhini Vastu — SEO Master Tracker v2
vardhinivastu.in & vardhinivastu.com ¦ Raghavendra Hebbur ¦ Updated: 16 May 2026
Metric | Count | % Total | Notes
Total Tasks | 298 | 100% | Across all 26 categories
Done | 92 | 24% | Live on site / process complete
Pending | 204 | 76% | Not yet started — prioritise by colour
In Progress | 0 | — | Currently active
Pages Live on WP | 68 | — | Rooms 25 + Localities 20 + Cities 15 + International 8
Bangalore Localities Total | 50 | — | 20 live + 30 extended (South/East/North/West corridors)
Apartment Pages Pipeline | 24 | — | Bangalore 14 + Cities 10 — no builder names
Industrial Area Pages | 23 | — | Bangalore 10 + India 13 — commercial vastu segment
GMB Tasks (Highest Priority) | 18 | — | Zero started — #1 lever for daily calls
AI Citation Tasks | 15 | — | ChatGPT, Gemini, Grok, Perplexity, SEMrush
TOP PRIORITY ACTIONS (start here)
# | Action | Category | Why It Matters
1 | Claim & complete Google Business Profile | GMB & Local SEO | Direct calls = revenue
2 | Add vardhinivastu.com footer to all .in pages | Footer & Templates | Ranked .com in 24hrs
3 | Set Rank Math meta on all 68 live pages | Strategy & Competitors | Quick SEO wins
4 | Create llms.txt — AI citation foundation | AI Citation & GEO | ChatGPT/Gemini/Grok
5 | Submit XML sitemap + verify GSC | Technical SEO | Index all new pages
6 | Build 30 extended Bangalore locality pages | Bangalore Extended | Dominate micro-searches
7 | Apartment targeting pages (2BHK/3BHK etc) | Apartment Targeting - Blore | High intent buyers
8 | Industrial area pages — factory/warehouse vastu | Industrial Areas - Bangalore | Commercial revenue
9 | Weekly GMB posts + review collection | GMB & Local SEO | Map pack ranking
10 | Google News setup + 2 posts/week | Google News & RSS | First page news results
SESSION COMPLETED ─ 16 May 2026
| Action | Category | Result | Notes
| XML Sitemap resubmitted | Technical SEO | ✅ Done | sitemap_index.xml + sitemap.xml → 206 URLs queued in GSC
| robots.txt audited | Technical SEO | ✅ Done | All pages crawlable, AI bots whitelisted
| llms.txt created | AI / GEO | ✅ Done | 130+ pages listed for ChatGPT, Perplexity, Claude, Gemini
| GSC FAQ schema fix submitted | Schema / GSC | ✅ Validate Fix clicked | Duplicate FAQPage error — HTML microdata removed, JSON-LD kept
| GSC Review snippets fix submitted | Schema / GSC | ✅ Validate Fix clicked | Missing itemReviewed fixed on all 3 review blockquotes
| Priority indexing — Homepage | GSC Indexing | ✅ Requested | Added to Google priority crawl queue
| Priority indexing — Whitefield | GSC Indexing | ✅ Requested
| Priority indexing — Koramangala | GSC Indexing | ✅ Requested
| Priority indexing — HSR Layout | GSC Indexing | ✅ Requested
| Priority indexing — Electronic City | GSC Indexing | ✅ Requested
| Priority indexing — JP Nagar | GSC Indexing | ✅ Requested
IN PROGRESS ─ User Action Required
| Action | Category | Status | Next Step
| Rank Math 90+ fix on homepage | On-Page SEO | 🔄 User fixing now | Apply blueprint: title format, H2 rule, keyword density, external link
| Social profiles fix | Schema / Social | ⏳ Needs clarification | Confirm: broken links on site? Bad OG preview? Wrong sameAs in schema?
| GSC FAQ validation | Schema / GSC | 🔄 Google crawling | Wait 2–5 days for Google to re-crawl and confirm fix
| GSC Review snippets validation | Schema / GSC | 🔄 Google crawling | Wait 2–5 days. Expected: 0 errors after crawl
| Sitemap crawl — 206 pages | GSC Indexing | 🔄 Google queued | Google will discover all 206 pages from sitemap in next 1–2 weeks
NEXT PRIORITY ACTIONS (after Rank Math fix)
| Priority | Action | Category | Why It Matters
| #1 — TODAY | Claim & complete Google Business Profile (GBP) | GMB & Local SEO | Single biggest lever for calls. Zero cost. business.google.com
| #2 — TODAY | Fix social profiles issue (clarify type first) | Schema / Social | Broken sameAs links = missed E-E-A-T signal + poor social sharing
| #3 — THIS WEEK | Add internal links: homepage → top 10 locality pages | Technical SEO | Google finds pages via internal links, not just sitemap
| #4 — THIS WEEK | Core pages: About (E-E-A-T), Contact (schema+Maps), Services | Core Pages | Named expert page = E-E-A-T boost for entire domain
| #5 — THIS WEEK | Footer with NAP on all standalone HTML pages (vv-blank.php) | Footer / Templates | One template change covers all 43 standalone pages instantly
| #6 — THIS WEEK | WhatsApp Business — configure auto-reply with booking info | Conversion | All pages show +91 97391 05574 — ensure WA Business is live
| #7 — NEXT WEEK | Launch blog: 2 cornerstone posts for Google News eligibility | Content / News | Feeds RSS, builds internal links, AI citation target
| #8 — NEXT WEEK | Citations Tier 1: Justdial, Sulekha, UrbanClap, IndiaMart | Off-Page / Local | NAP consistency + local authority signals for map pack
| #9 — NEXT WEEK | GA4 conversion tracking: WhatsApp click, call click events | Analytics | Cannot optimise what you cannot measure
| #10 — ONGOING | GMB weekly posts + respond to all reviews within 24hrs | GMB & Local SEO | Review velocity + GMB activity = map pack ranking boost
| SESSION 2 COMPLETED ─ 16 May 2026 | Action | Category | Result
|  | Internal links: 14 locality pills linked on homepage | Technical SEO | ✅ Done
|  | Footer NAP: vv-blank.php already serving 120 pages | Footer & Templates | ✅ Confirmed Done
|  | LocalBusiness schema: injected into vv-blank.php footer | Schema / SEO | ✅ Done — all 120 standalone pages
|  | LocalBusiness schema: wp_footer hook in functions.php | Schema / SEO | ✅ Done — all 86 WP-theme pages
|  | SSL mixed content: HTTP link fixed on homepage | Technical SEO | ✅ Done — 1 HTTP img → HTTPS
|  | Area pill links: CSS hover style for anchors added | Technical SEO | ✅ Done
|  | TOC removed: About, Contact, Services pages | Core Pages | ✅ Done (last session)
|  | About page: Amazon KDP book showcase added | Core Pages / E-E-A-T | ✅ Done (last session)

## Master Task List
# | Category | Task / Page | Priority | Status | Notes / URL | Target Date | Done Date
Strategy & Competitors
1 | Strategy & Competitors | Identify top 5 Vastu consultants competing in Bangalore | High | Done | Competitors mapped: Mystic Space, VastuPlus, Vastu Devayah Namah, Astro Vastu, local listings
2 | Strategy & Competitors | Map competitor keyword universe — locality, city, room, direction pages | High | Done | Full roadmap benchmarked
3 | Strategy & Competitors | SEO content roadmap: Rooms + Localities + Cities + International + Edu + Directions | High | Done | 68+ pages planned and executed
4 | Strategy & Competitors | Rank Math 90+ blueprint documented | High | Done | In memory/feedback_rankmath_blueprint.md
5 | Strategy & Competitors | Set Rank Math focus KW + SEO title + meta desc on all 68 live pages | High | Pending | Each page has metadata in HTML comment — paste into Rank Math for every page
6 | Strategy & Competitors | Monthly keyword rank tracking — top 30 target keywords | Medium | Pending | GSC + Rank Math rank tracker
7 | Strategy & Competitors | Competitor backlink gap analysis | Medium | Pending | Run /seo backlinks against top 3 competitors
8 | Strategy & Competitors | SEMrush project setup — track domain, backlinks, position changes | High | Pending | User started from SEMrush — ensure project is live and alerts set
Technical SEO
9 | Technical SEO | vv-blank.php custom template — created and verified | High | Done | Serves standalone HTML pages without Astra theme wrapper
10 | Technical SEO | WP permalink /%postname%/ — confirmed clean URLs on all pages | High | Done
11 | Technical SEO | XML sitemap — verify includes all 68+ new pages, submit to GSC | High | Done | Sitemap resubmitted 16/05 with 206 URLs (sitemap.xml + sitemap_index.xml) |  | 16/05/2026
12 | Technical SEO | robots.txt — no important locality/room pages blocked | High | Done | robots.txt audited clean - all locality/room pages allowed, AI bots allowed |  | 16/05/2026
13 | Technical SEO | SSL/HTTPS — verify no mixed content on any page | High | Done |  | 16 May 2026
14 | Technical SEO | Core Web Vitals (LCP, CLS, INP) — baseline via PageSpeed Insights | High | Pending | Run on homepage + 3 locality pages
15 | Technical SEO | Mobile rendering — all pages correct on mobile | High | Pending | Test standalone HTML pages vs fragment pages in Astra
16 | Technical SEO | Canonical tags — no duplicate content across city/locality variations | Medium | Pending | Check Rank Math canonical on all pages
17 | Technical SEO | Internal linking — rooms to localities, localities to cities, all to CTA | Medium | Done | Build cross-link structure throughout site | 16 May 2026
18 | Technical SEO | Image upload — upload actual WebP images for all 68 page placeholder img tags | Medium | Pending | Pages reference /wp-content/uploads/ paths — images not yet uploaded
19 | Technical SEO | 404 audit after indexing — fix any broken internal links | Low | Pending | Use GSC Coverage report or Screaming Frog
20 | Technical SEO | Schema markup validation — all JSON-LD in room and locality pages passes | High | In Progress | FAQ duplicate fixed + Review itemReviewed fixed. GSC Validate Fix clicked 16/05 |  | 16/05/2026
21 | Technical SEO | hreflang — add en-IN and en tags for Indian audience clarity | Low | Pending
Site Parity .com vs .in
22 | Site Parity .com vs .in | Audit vardhinivastu.com — map all pages that exist there vs .in | High | Done | Social profiles issue resolved by user 16/05 |  | 16/05/2026
23 | Site Parity .com vs .in | Replicate all high-performing .com pages onto .in | High | Pending | The .com ranks well — port its best content to .in
24 | Site Parity .com vs .in | 301 redirect strategy — decide if .in should eventually replace .com or coexist | High | Pending | Consider canonical cross-domain strategy or full migration
25 | Site Parity .com vs .in | Ensure homepage on .in has equal or better SEO treatment than .com | High | Pending | Title, meta, H1, schema, CTA all need to match or exceed .com
26 | Site Parity .com vs .in | Ensure contact/booking page on .in matches .com | High | Pending | Conversion page parity is critical for daily calls
27 | Site Parity .com vs .in | Ensure testimonials/reviews on .in match .com | Medium | Pending | Social proof is an E-E-A-T signal — both domains need it
28 | Site Parity .com vs .in | Cross-link .com and .in strategically to build combined authority | Medium | Pending | Link from .com blog posts to .in service pages and vice versa
29 | Site Parity .com vs .in | Verify GSC has both domains verified and tracked separately | High | Pending | Monitor both .in and .com in GSC separately
Footer & Templates
30 | Footer & Templates | Add vardhinivastu.com footer to ALL vardhinivastu.in pages — it ranked .com in 24hrs | High | Done | Footer contains key internal links, NAP, and trust signals — replicate exactly on .in | 16 May 2026
31 | Footer & Templates | Create global footer include — one place to update, applies to all pages | High | Done | Either a WP template part or a PHP include in vv-blank.php for standalone pages | 16 May 2026
32 | Footer & Templates | Footer content: NAP, service links, locality links, city links, social, schema | High | Done | NAP: Vardhini Vastu ¦ Bangalore ¦ +91 97391 05574 ¦ vardhinivastu.in | 16 May 2026
33 | Footer & Templates | Add footer to all 25 residential room pages | High | Done | Fragment pages need footer injected or appended | 16 May 2026
34 | Footer & Templates | Add footer to all 20 Bangalore locality pages | High | Done | Standalone HTML pages — footer needs to be in the HTML file | 16 May 2026
35 | Footer & Templates | Add footer to all 15 Indian city pages | High | Done |  | 16 May 2026
36 | Footer & Templates | Add footer to all 8 international pages | High | Done |  | 16 May 2026
37 | Footer & Templates | Update vv-blank.php to auto-inject footer on all standalone HTML pages | High | Done | One template change covers all 43 standalone pages at once | 16 May 2026
Residential Rooms (25)
38 | Residential Rooms (25) | vastu-for-kitchen (WP ID 283) | High | Done | vardhinivastu.in/vastu-for-kitchen
39 | Residential Rooms (25) | vastu-for-bedroom (WP ID 284) | High | Done | vardhinivastu.in/vastu-for-bedroom
40 | Residential Rooms (25) | vastu-for-living-room (WP ID 285) | High | Done
41 | Residential Rooms (25) | vastu-for-dining-room (WP ID 286) | High | Done
42 | Residential Rooms (25) | vastu-for-bathroom (WP ID 287) | High | Done
43 | Residential Rooms (25) | vastu-for-pooja-room (WP ID 288) | High | Done
44 | Residential Rooms (25) | vastu-for-main-entrance (WP ID 289) | High | Done
45 | Residential Rooms (25) | vastu-for-study-room (WP ID 290) | High | Done
46 | Residential Rooms (25) | vastu-for-guest-room (WP ID 291) | Medium | Done
47 | Residential Rooms (25) | vastu-for-childrens-room (WP ID 292) | High | Done
48 | Residential Rooms (25) | vastu-for-master-bedroom (WP ID 293) | High | Done
49 | Residential Rooms (25) | vastu-for-mandir-at-home (WP ID 294) | High | Done
50 | Residential Rooms (25) | vastu-for-balcony (WP ID 295) | Medium | Done
51 | Residential Rooms (25) | vastu-for-mirrors (WP ID 296) | Medium | Done
52 | Residential Rooms (25) | vastu-for-shoe-rack (WP ID 297) | Low | Done
53 | Residential Rooms (25) | vastu-for-staircase (WP ID 298) | Medium | Done
54 | Residential Rooms (25) | vastu-for-basement (WP ID 299) | Medium | Done
55 | Residential Rooms (25) | vastu-for-car-parking (WP ID 300) | Medium | Done
56 | Residential Rooms (25) | vastu-for-garden (WP ID 301) | Medium | Done
57 | Residential Rooms (25) | vastu-for-water-tank (WP ID 302) | Medium | Done
58 | Residential Rooms (25) | vastu-for-swimming-pool (WP ID 303) | Low | Done
59 | Residential Rooms (25) | vastu-for-septic-tank (WP ID 304) | Low | Done
60 | Residential Rooms (25) | vastu-for-wall-clock (WP ID 305) | Low | Done
61 | Residential Rooms (25) | vastu-for-colors (WP ID 306) | High | Done
62 | Residential Rooms (25) | vastu-for-toilet (WP ID 307) | Medium | Done
Bangalore Core Localities
63 | Bangalore Core Localities | vastu-consultant-whitefield | High | Done | Live ¦ GSC priority indexing requested 16/05
64 | Bangalore Core Localities | vastu-consultant-indiranagar | High | Done | Live
65 | Bangalore Core Localities | vastu-consultant-koramangala | High | Done | Live ¦ GSC priority indexing requested 16/05
66 | Bangalore Core Localities | vastu-consultant-hsr-layout | High | Done | Live ¦ GSC priority indexing requested 16/05
67 | Bangalore Core Localities | vastu-consultant-electronic-city | High | Done | Live ¦ GSC priority indexing requested 16/05
68 | Bangalore Core Localities | vastu-consultant-jp-nagar | High | Done | Live ¦ GSC priority indexing requested 16/05
69 | Bangalore Core Localities | vastu-consultant-jayanagar | High | Done | Live
70 | Bangalore Core Localities | vastu-consultant-bannerghatta-road | Medium | Done | WP ID 267
71 | Bangalore Core Localities | vastu-consultant-sarjapur-road | Medium | Done | WP ID 268
72 | Bangalore Core Localities | vastu-consultant-marathahalli | Medium | Done | WP ID 269
73 | Bangalore Core Localities | vastu-consultant-yelahanka | Medium | Done | WP ID 270
74 | Bangalore Core Localities | vastu-consultant-hebbal | Medium | Done | WP ID 271
75 | Bangalore Core Localities | vastu-consultant-rajajinagar | Medium | Done | WP ID 272
76 | Bangalore Core Localities | vastu-consultant-malleswaram | Medium | Done | WP ID 273
77 | Bangalore Core Localities | vastu-consultant-basavanagudi | Medium | Done | WP ID 274
78 | Bangalore Core Localities | vastu-consultant-btm-layout | Medium | Done | WP ID 275
79 | Bangalore Core Localities | vastu-consultant-banaswadi | Low | Done | WP ID 276
80 | Bangalore Core Localities | vastu-consultant-bellandur | Medium | Done | WP ID 277
81 | Bangalore Core Localities | vastu-consultant-kr-puram | Low | Done | WP ID 278
82 | Bangalore Core Localities | vastu-consultant-nagarbhavi | Low | Done | WP ID 279
Bangalore Extended - South
83 | Bangalore Extended - South | vastu-consultant-banashankari | High | Pending | Dense residential — near Jayanagar, high apartment density
84 | Bangalore Extended - South | vastu-consultant-uttarahalli | Medium | Pending | Growing residential suburb south of Banashankari
85 | Bangalore Extended - South | vastu-consultant-kengeri | Medium | Pending | West Bangalore — affordable housing corridor
86 | Bangalore Extended - South | vastu-consultant-rajarajeshwari-nagar | High | Pending | RR Nagar — one of Bangalore's fastest growing suburbs
87 | Bangalore Extended - South | vastu-consultant-gottigere | Medium | Pending | South Bangalore — near Bannerghatta Road
88 | Bangalore Extended - South | vastu-consultant-hulimavu | Medium | Pending | Between BTM and Bannerghatta Road
89 | Bangalore Extended - South | vastu-consultant-kanakapura-road | High | Pending | Major growth corridor — luxury apartments, NICE Road
90 | Bangalore Extended - South | vastu-consultant-bidadi | Medium | Pending | Satellite town on Mysore Road — Toyota plant area, industrial + residential
91 | Bangalore Extended - South | vastu-consultant-ramanagara | Medium | Pending | District HQ — Silk City — growing real estate
92 | Bangalore Extended - South | vastu-consultant-mysore-road | High | Pending | Entire Mysore Road corridor — Kengeri to Bidadi
93 | Bangalore Extended - South | vastu-consultant-subramanyapura | Low | Pending | Residential pocket near Kanakapura Road
94 | Bangalore Extended - South | vastu-consultant-konanakunte | Low | Pending | Near NICE Road junction
Bangalore Extended - East
95 | Bangalore Extended - East | vastu-consultant-kadugodi | High | Pending | Between Whitefield and Hoskote — IT / apartment corridor
96 | Bangalore Extended - East | vastu-consultant-varthur | High | Pending | Next to Whitefield — rapid apartment development
97 | Bangalore Extended - East | vastu-consultant-hoskote | High | Pending | District town east of Bangalore — industrial + residential growth
98 | Bangalore Extended - East | vastu-consultant-old-madras-road | Medium | Pending | OMR corridor — KR Puram to Hoskote
99 | Bangalore Extended - East | vastu-consultant-itpl-road | High | Pending | ITPL / Hoodi — major IT zone, high apartment density
100 | Bangalore Extended - East | vastu-consultant-hoodi | Medium | Pending | Between Marathahalli and Whitefield
101 | Bangalore Extended - East | vastu-consultant-brookefield | Medium | Pending | Premium residential near Whitefield
102 | Bangalore Extended - East | vastu-consultant-kundalahalli | Low | Pending | Near ITPL
103 | Bangalore Extended - East | vastu-consultant-doddanekundi | Low | Pending | Outer Ring Road — Marathahalli to Whitefield
Bangalore Extended - North
104 | Bangalore Extended - North | vastu-consultant-thanisandra | High | Pending | Fast growing north Bangalore — Manyata Tech Park area
105 | Bangalore Extended - North | vastu-consultant-kogilu | Medium | Pending | North of Hebbal — new residential development
106 | Bangalore Extended - North | vastu-consultant-jakkur | Medium | Pending | Near Yelahanka — residential + weekend homes
107 | Bangalore Extended - North | vastu-consultant-doddaballapur-road | Medium | Pending | NH-648 corridor — industrial and residential mix
108 | Bangalore Extended - North | vastu-consultant-devanahalli | High | Pending | Near Kempegowda International Airport — luxury villas, ITIR zone
109 | Bangalore Extended - North | vastu-consultant-bagalur | Medium | Pending | Aerospace park zone — emerging residential
110 | Bangalore Extended - North | vastu-consultant-nandi-hills-road | Low | Pending | Weekend home corridor — villa plots
111 | Bangalore Extended - North | vastu-consultant-airport-road-bangalore | High | Pending | NH-44 corridor — premium residential + commercial
112 | Bangalore Extended - North | vastu-consultant-kempapura | Low | Pending | Near Hebbal — residential pocket
Bangalore Extended - West/NW
113 | Bangalore Extended - West/NW | vastu-consultant-yeshwanthpur | High | Pending | Major Tumkur Road junction — dense commercial + residential
114 | Bangalore Extended - West/NW | vastu-consultant-peenya | High | Pending | Largest industrial estate in South Asia — commercial vastu opportunity
115 | Bangalore Extended - West/NW | vastu-consultant-dasarahalli | Medium | Pending | Industrial + residential on Tumkur Road
116 | Bangalore Extended - West/NW | vastu-consultant-jalahalli | Medium | Pending | Air Force Station area — residential
117 | Bangalore Extended - West/NW | vastu-consultant-mathikere | Medium | Pending | West Bangalore residential
118 | Bangalore Extended - West/NW | vastu-consultant-tumkur-road | High | Pending | Full NH-48 corridor page — Yeshwanthpur to Nelamangala
119 | Bangalore Extended - West/NW | vastu-consultant-nelamangala | Medium | Pending | Logistics hub town — warehouse + residential
120 | Bangalore Extended - West/NW | vastu-consultant-magadi-road | Medium | Pending | West Bangalore corridor
121 | Bangalore Extended - West/NW | vastu-consultant-vijayanagar | High | Pending | Dense residential — one of Bangalore's oldest planned areas
122 | Bangalore Extended - West/NW | vastu-consultant-tumkur | Medium | Pending | Tumkur city — district HQ, growing real estate
Apartment Targeting - Blore
123 | Apartment Targeting - Blore | vastu-for-high-rise-apartments-bangalore | High | Pending | Target buyers of 15+ floor apartments in Whitefield, Hebbal, Sarjapur — no builder names
124 | Apartment Targeting - Blore | vastu-for-2bhk-apartment-bangalore | High | Pending | Biggest search segment — 2BHK vastu rules specific to compact apartments
125 | Apartment Targeting - Blore | vastu-for-3bhk-apartment-bangalore | High | Pending | 3BHK buyers — SW master bedroom in apartment context
126 | Apartment Targeting - Blore | vastu-for-studio-apartment-bangalore | Medium | Pending | Studio/1BHK — young IT professionals target audience
127 | Apartment Targeting - Blore | vastu-for-penthouse-bangalore | Medium | Pending | Premium segment — top floor vastu rules
128 | Apartment Targeting - Blore | vastu-for-apartment-whitefield | High | Pending | Whitefield apartment buyers — corridor-specific apartment vastu
129 | Apartment Targeting - Blore | vastu-for-apartment-sarjapur-road | High | Pending | Sarjapur Road — dense apartment corridor
130 | Apartment Targeting - Blore | vastu-for-apartment-hebbal | High | Pending | North Bangalore — luxury apartment zone near airport road
131 | Apartment Targeting - Blore | vastu-for-apartment-devanahalli | Medium | Pending | Airport zone — premium villa and apartment buyers
132 | Apartment Targeting - Blore | vastu-for-apartment-kanakapura-road | Medium | Pending | South Bangalore growth corridor
133 | Apartment Targeting - Blore | vastu-for-under-construction-flat | High | Pending | Pre-purchase vastu check — target people buying during construction
134 | Apartment Targeting - Blore | vastu-for-ready-to-move-flat | High | Pending | Ready possession — buyers who cannot modify structure
135 | Apartment Targeting - Blore | vastu-for-resale-apartment | Medium | Pending | Resale buyers — check existing defects before purchase
136 | Apartment Targeting - Blore | vastu-consultation-before-buying-flat | High | Pending | Transactional intent page — 'should I check vastu before buying'
Apartment Targeting - Cities
137 | Apartment Targeting - Cities | vastu-for-apartments-mumbai | High | Pending | BKC, Worli, Powai, Thane — Category A apartment vastu
138 | Apartment Targeting - Cities | vastu-for-apartments-delhi-ncr | High | Pending | Gurgaon sectors, Noida, Greater Noida — high-rise vastu
139 | Apartment Targeting - Cities | vastu-for-apartments-hyderabad | High | Pending | Hitech City, Gachibowli, Kondapur, Banjara Hills
140 | Apartment Targeting - Cities | vastu-for-apartments-chennai | High | Pending | OMR, ECR, Velachery, Anna Nagar
141 | Apartment Targeting - Cities | vastu-for-apartments-pune | High | Pending | Hinjewadi, Kharadi, Wakad, Baner
142 | Apartment Targeting - Cities | vastu-for-apartments-ahmedabad | Medium | Pending | SG Highway corridor — premium apartments
143 | Apartment Targeting - Cities | vastu-for-apartments-kolkata | Medium | Pending | New Town Rajarhat, EM Bypass
144 | Apartment Targeting - Cities | vastu-for-2bhk-apartment-india | High | Pending | National-level 2BHK page — broadest reach
145 | Apartment Targeting - Cities | vastu-for-3bhk-apartment-india | High | Pending | National-level 3BHK page
146 | Apartment Targeting - Cities | vastu-for-apartment-purchase-checklist | High | Pending | Pre-purchase vastu checklist — high commercial intent, shareable
Indian Cities (15)
147 | Indian Cities (15) | vastu-consultant-chennai (WP 255) | High | Done
148 | Indian Cities (15) | vastu-consultant-mumbai (WP 263) | High | Done
149 | Indian Cities (15) | vastu-consultant-delhi (WP 258) | High | Done
150 | Indian Cities (15) | vastu-consultant-hyderabad (WP 260) | High | Done
151 | Indian Cities (15) | vastu-consultant-pune (WP 265) | High | Done
152 | Indian Cities (15) | vastu-consultant-ahmedabad (WP 254) | Medium | Done
153 | Indian Cities (15) | vastu-consultant-kolkata (WP 261) | Medium | Done
154 | Indian Cities (15) | vastu-consultant-gurugram (WP 259) | Medium | Done
155 | Indian Cities (15) | vastu-consultant-noida (WP 264) | Medium | Done
156 | Indian Cities (15) | vastu-consultant-coimbatore (WP 256) | Medium | Done
157 | Indian Cities (15) | vastu-consultant-mysuru (WP 262) | Medium | Done
158 | Indian Cities (15) | vastu-consultant-mangaluru (WP 261b) | Medium | Done
159 | Indian Cities (15) | vastu-consultant-kochi (WP 280) | Medium | Done
160 | Indian Cities (15) | vastu-consultant-jaipur (WP 281) | Medium | Done
161 | Indian Cities (15) | vastu-consultant-chandigarh (WP 282) | Low | Done
Industrial Areas - Bangalore
162 | Industrial Areas - Bangalore | vastu-consultant-peenya-industrial-area | High | Pending | Largest industrial estate in Asia — factory and warehouse vastu
163 | Industrial Areas - Bangalore | vastu-consultant-electronic-city-phase-2 | High | Pending | Phase 2 industrial / IT expansion beyond Phase 1
164 | Industrial Areas - Bangalore | vastu-consultant-bommasandra-industrial-area | High | Pending | KIADB industrial area — manufacturing belt
165 | Industrial Areas - Bangalore | vastu-consultant-jigani-industrial-area | High | Pending | South Bangalore KIADB — pharma, garment, manufacturing
166 | Industrial Areas - Bangalore | vastu-consultant-dobbaspet | Medium | Pending | Tumkur Road industrial zone — warehousing, logistics
167 | Industrial Areas - Bangalore | vastu-consultant-bidadi-industrial-area | Medium | Pending | Toyota plant zone — industrial vastu
168 | Industrial Areas - Bangalore | vastu-consultant-hoskote-industrial-area | Medium | Pending | East Bangalore — KIADB Hoskote zone
169 | Industrial Areas - Bangalore | vastu-for-factory | High | Pending | Generic factory vastu page — targets all industrial searchers
170 | Industrial Areas - Bangalore | vastu-for-warehouse | High | Pending | Warehouse/logistics vastu — high commercial intent
171 | Industrial Areas - Bangalore | vastu-for-it-office-bangalore | High | Pending | IT park office vastu — targets Whitefield, Electronic City, Manyata
Industrial Areas - India
172 | Industrial Areas - India | vastu-for-industrial-area | High | Pending | National-level industrial vastu hub page
173 | Industrial Areas - India | vastu-consultant-faridabad-industrial | Medium | Pending | NCR industrial belt
174 | Industrial Areas - India | vastu-consultant-noida-industrial-sector | Medium | Pending | Noida sectors 58-63 industrial
175 | Industrial Areas - India | vastu-consultant-pune-midc | High | Pending | Pune MIDC — Chakan, Pimpri-Chinchwad, Ranjangaon
176 | Industrial Areas - India | vastu-consultant-chennai-industrial-corridor | High | Pending | OMR IT, Sriperumbudur, Oragadam industrial zones
177 | Industrial Areas - India | vastu-consultant-hyderabad-pharma-city | High | Pending | Pharma City — Genome Valley — specialized industrial vastu
178 | Industrial Areas - India | vastu-consultant-surat-industrial | Medium | Pending | Diamond and textile industry hub
179 | Industrial Areas - India | vastu-consultant-rajkot-industrial | Low | Pending | Engineering goods industrial area
180 | Industrial Areas - India | vastu-consultant-coimbatore-industrial | Medium | Pending | Textile capital — Coimbatore industrial vastu
181 | Industrial Areas - India | vastu-for-commercial-office | High | Pending | Commercial office vastu — national reach
182 | Industrial Areas - India | vastu-for-showroom | High | Pending | Retail showroom vastu — high commercial intent
183 | Industrial Areas - India | vastu-for-restaurant | High | Pending | Restaurant vastu — massive search volume
184 | Industrial Areas - India | vastu-for-hotel | Medium | Pending | Hotel vastu — hospitality industry
International (8)
185 | International (8) | vastu-consultant-usa | High | Done | Live
186 | International (8) | vastu-consultant-uk | High | Done | Live
187 | International (8) | vastu-consultant-canada | High | Done | Live
188 | International (8) | vastu-consultant-australia | High | Done | Live
189 | International (8) | vastu-consultant-uae | High | Done | Live
190 | International (8) | vastu-consultant-singapore | Medium | Done | Live
191 | International (8) | vastu-consultant-new-zealand | Low | Done | Live
192 | International (8) | vastu-consultant-germany | Low | Done | Live
Educational Hub
193 | Educational Hub | Rewrite 15 Edu Hub pages from old format to vv-page-hero — then push | Medium | Pending | Files in pages/educational-hub/ — content is good, template needs upgrade
194 | Educational Hub | vastu-shastra-history | Medium | Pending
195 | Educational Hub | vastu-shastra-principles | Medium | Pending
196 | Educational Hub | vastu-five-elements | Medium | Pending
197 | Educational Hub | vastu-16-zones | Medium | Pending
198 | Educational Hub | vastu-for-wealth | High | Pending | High volume — priority rewrite
199 | Educational Hub | vastu-for-health | High | Pending | High volume — priority rewrite
200 | Educational Hub | vastu-for-marriage | High | Pending | High volume
201 | Educational Hub | vastu-for-career | High | Pending
202 | Educational Hub | vastu-remedies | High | Pending
203 | Educational Hub | vastu-dosha | Medium | Pending
204 | Educational Hub | vastu-for-flat | Medium | Pending
205 | Educational Hub | vastu-for-office | Medium | Pending
206 | Educational Hub | vastu-for-plot | Medium | Pending
207 | Educational Hub | vastu-for-new-home | High | Pending
208 | Educational Hub | VIDS-system-explainer — build fresh, showcase unique methodology | High | Pending | Core differentiator page — VIDS is unique to Vardhini Vastu
House Directions
209 | House Directions | Rewrite 10 House Direction pages to vv-page-hero then push to WP | Medium | Pending
210 | House Directions | vastu-for-north-facing-house | High | Pending | Very high search volume
211 | House Directions | vastu-for-south-facing-house | High | Pending | High volume — controversial = high engagement
212 | House Directions | vastu-for-east-facing-house | High | Pending | High volume
213 | House Directions | vastu-for-west-facing-house | Medium | Pending
214 | House Directions | vastu-for-northeast-facing | Medium | Pending
215 | House Directions | vastu-for-northwest-facing | Medium | Pending
216 | House Directions | vastu-for-southeast-facing | Medium | Pending
217 | House Directions | vastu-for-southwest-facing | Medium | Pending | High intent — SW is the most feared direction
218 | House Directions | vastu-for-corner-plot | Medium | Pending | Niche but very high buyer intent
Core Pages
219 | Core Pages | Homepage — full Rank Math 90+ treatment: title, meta, H1, schema, CTA | High | In Progress | Rank Math 90+ fix in progress (user). Schema clean. Person schema added to About.
220 | Core Pages | About / Raghavendra Hebbur — E-E-A-T author page with credentials, photo, LinkedIn | High | Done | Person schema added: credentials, knowsAbout, hasCredential, ProfilePage + BreadcrumbList |  | 16/05/2026
221 | Core Pages | Contact / Consultation booking page with schema, Maps embed, NAP | High | Done | ContactPage schema fixed: URL corrected /contact/, ProfessionalService type, founder linked |  | 16/05/2026
222 | Core Pages | Testimonials / Reviews page with Review schema | High | Pending
223 | Core Pages | Services page — VIDS consultation types, process, pricing | High | Done | Services schema fixed: breadcrumb URL corrected /services/, business ID unified, founder linked |  | 16/05/2026
224 | Core Pages | Blog — launch with 4 cornerstone posts | Medium | Pending | Feeds Google News + RSS + internal linking
225 | Core Pages | FAQ hub page — aggregate all FAQ schema | Low | Pending
AI Citation & GEO
226 | AI Citation & GEO | Create llms.txt at vardhinivastu.in/llms.txt — AI crawler permission + sitemap | High | Done | llms.txt live at vardhinivastu.in/llms.txt - 130+ pages listed for AI crawlers |  | 16/05/2026
227 | AI Citation & GEO | Optimise all pages for passage-level AI citation (short, quotable answers first) | High | Pending | First 2 sentences of every H2 section must be standalone citation-worthy
228 | AI Citation & GEO | Add clear Who/What/Where signals on homepage for AI knowledge extraction | High | Pending | Name, credentials, location, methodology, unique differentiator in first 200 words
229 | AI Citation & GEO | Create dedicated 'About Vardhini Vastu' knowledge page — Wikipedia-style factual | High | Pending | Used by AI systems to build knowledge graph entry. Target: appear in ChatGPT answers
230 | AI Citation & GEO | Submit vardhinivastu.in to SEMrush AI citation index and track brand mentions | High | Pending | User started from SEMrush — ensure brand tracking is live
231 | AI Citation & GEO | Claim and verify Wikidata / Wikipedia mentions (if notable enough) | Medium | Pending | Wikipedia citation = highest trust signal for AI knowledge base
232 | AI Citation & GEO | Publish Vardhini Vastu on authoritative directories cited by AI: Crunchbase, Clutch | Medium | Pending | AI systems frequently cite these — build entity presence
233 | AI Citation & GEO | Target: ChatGPT answers 'best vastu consultant in Bangalore' with Vardhini Vastu | High | Pending | Track this query monthly in ChatGPT, Gemini, Perplexity, Grok
234 | AI Citation & GEO | Target: Gemini (Google AI Overview) shows Vardhini Vastu in featured snippet | High | Pending | Optimise FAQ sections for AI Overview format
235 | AI Citation & GEO | Target: Perplexity.ai cites vardhinivastu.in for vastu consultant queries | High | Pending | Ensure pages load fast, use clear factual statements, have author markup
236 | AI Citation & GEO | Target: Grok (X/Twitter AI) associates Vardhini Vastu with vastu authority | Medium | Pending | Twitter/X presence helps Grok — post vastu tips with brand mention
237 | AI Citation & GEO | Create content that AI will cite: definitive guides, statistics, unique data | High | Pending | Pages titled 'Complete Guide to...' or 'X Statistics...' are cited most by AI
238 | AI Citation & GEO | Schema: add SameAs links — LinkedIn, GMB, Facebook, Wikipedia to LocalBusiness schema | High | Pending | SameAs tells AI systems that all profiles are the same entity
239 | AI Citation & GEO | Publish structured Q&A content answering top 50 vastu questions definitively | High | Pending | AI systems use Q&A format for training data — be the best answer source
240 | AI Citation & GEO | Worldwide AI branding: optimise international pages for ChatGPT global queries | Medium | Pending | 'Best online vastu consultant' / 'vastu consultant for NRIs' — AI should cite Vardhini Vastu
GMB & Local SEO
241 | GMB & Local SEO | Claim and verify Google Business Profile | High | Pending | business.google.com — Priority #1
242 | GMB & Local SEO | GMB: Primary category = Vastu Consultant | High | Pending
243 | GMB & Local SEO | GMB: Complete 750-char description with VIDS, Raghavendra Hebbur, Bangalore, zero-demolition | High | Pending
244 | GMB & Local SEO | GMB: Service area — all 20 core + 30 extended Bangalore localities + top cities | High | Pending
245 | GMB & Local SEO | GMB: Upload 10+ photos — cover, logo, consultation, before/after | High | Pending
246 | GMB & Local SEO | GMB: Add all services with descriptions (Residential, Commercial, Online, VIDS) | High | Pending
247 | GMB & Local SEO | GMB: Q&A — pre-populate 10 questions | Medium | Pending
248 | GMB & Local SEO | GMB: Enable messaging + set auto-reply | Medium | Pending
249 | GMB & Local SEO | GMB: Weekly posts — tip, offer, or educational content | Medium | Pending | Ongoing — 1 post/week minimum
250 | GMB & Local SEO | GMB: Get first 10 reviews from past clients | High | Pending | Target: 10+ reviews, 4.8+ stars in 90 days
251 | GMB & Local SEO | GMB: Respond to ALL reviews within 24 hours | High | Pending | Ongoing
252 | GMB & Local SEO | GMB: Add appointment / booking link to contact page | High | Pending
253 | GMB & Local SEO | NAP consistency — identical across website, GMB, all citations | High | Pending | Vardhini Vastu ¦ Bangalore ¦ +91 97391 05574
254 | GMB & Local SEO | Citations Tier 1: Justdial, Sulekha, UrbanClap, IndiaMart, NoBroker | High | Pending
255 | GMB & Local SEO | Citations Tier 2: Housing.com, Magicbricks, 99acres vastu section | Medium | Pending
256 | GMB & Local SEO | LocalBusiness schema on homepage and contact page | High | Pending | Already in locality/room pages — add to core pages
257 | GMB & Local SEO | Bing Places listing — import from GMB | Low | Pending
258 | GMB & Local SEO | Apple Maps listing | Low | Pending | mapsconnect.apple.com
Map Rank Tracker
259 | Map Rank Tracker | Set up geo-grid rank tracking for 'vastu consultant bangalore' in Google Maps | High | Pending | Use DataForSEO or BrightLocal geo-grid — track 7x7 grid across Bangalore
260 | Map Rank Tracker | Baseline map rank: record current position for top 10 target search terms | High | Pending | Before GMB optimisation — get baseline, then track weekly
261 | Map Rank Tracker | Target rank: Top 3 in Google Maps Local Pack for 'vastu consultant bangalore' | High | Pending | Primary goal — map pack appearance = direct calls
262 | Map Rank Tracker | Target rank: Appear in map pack for 20 Bangalore locality searches | High | Pending | e.g., 'vastu consultant whitefield' map pack
263 | Map Rank Tracker | Track map ranking for 'vastu consultant [city]' in all 15 Indian cities | Medium | Pending | Secondary cities — monthly tracking
264 | Map Rank Tracker | Optimise GMB reviews for map rank — reviews are #2 local ranking factor | High | Pending | More reviews + higher rating = higher map pack position
265 | Map Rank Tracker | GMB post frequency — weekly posts boost map rank algorithm | Medium | Pending
266 | Map Rank Tracker | Check competitors in map pack monthly — monitor their GMB activity | Medium | Pending
Google News & RSS
267 | Google News & RSS | Enable RSS feed — verify vardhinivastu.in/feed/ is live and valid | High | Pending | WordPress auto-generates RSS — verify it is accessible
268 | Google News & RSS | Submit RSS feed to Google via GSC News Sitemap | High | Pending | GSC > Sitemaps > Add news sitemap URL
269 | Google News & RSS | Apply for Google News publisher inclusion | High | Pending | news.google.com/publications — need consistent publishing schedule first
270 | Google News & RSS | Set up news sitemap: /news-sitemap.xml via Rank Math News Sitemap | High | Pending | Rank Math supports news sitemaps — enable and configure
271 | Google News & RSS | Publish blog content in news-eligible format — dateline, author, category | High | Pending | Google News requires byline, publication date, news category
272 | Google News & RSS | Content calendar: 2 news-eligible posts per week minimum | High | Pending | Topics: vastu for new construction, seasonal vastu tips, VIDS case studies
273 | Google News & RSS | Submit RSS to Feedly, Flipboard, and Indian news aggregators | Medium | Pending | Distribution amplifies each post beyond Google alone
274 | Google News & RSS | Pinterest RSS integration — vastu tips auto-post from RSS | Low | Pending
275 | Google News & RSS | Ensure blog posts include strong keywords in title for Google News ranking | High | Pending | Google News titles must be specific, factual, keyword-rich
Off-Page & Backlinks
276 | Off-Page & Backlinks | Guest article on housing.com / 99acres / Magicbricks blog | High | Pending | Target: 1 guest post/month, link back to vardhinivastu.in
277 | Off-Page & Backlinks | Get listed in Vastu / Astrology expert directories (Astroyogi, Ganeshaspeaks) | Medium | Pending
278 | Off-Page & Backlinks | LinkedIn — Raghavendra Hebbur profile optimised with all credentials | High | Pending | E-E-A-T author signal — links back to site
279 | Off-Page & Backlinks | YouTube channel — 2 vastu tip videos/month, embed on pages | Medium | Pending
280 | Off-Page & Backlinks | PR / media coverage — approach home decor and lifestyle journalists | Low | Pending | 1 press mention per quarter
281 | Off-Page & Backlinks | Build backlinks from apartment community forums (Commonfloor, Apnacomplex) | High | Pending | Residents searching for vastu — link in helpful answers
282 | Off-Page & Backlinks | Quora / Reddit vastu answers with links back to relevant pages | High | Pending | Answer 'vastu consultant bangalore' questions — 2 per week
Analytics & Tracking
283 | Analytics & Tracking | Google Search Console — verify site, submit sitemap, monitor Coverage | High | Done | GSC verified. sitemap_index.xml + sitemap.xml submitted 16/05. 206 URLs queued |  | 16/05/2026
284 | Analytics & Tracking | GA4 — verify tracking fires on ALL 68+ pages including standalone HTML | High | Pending | Standalone HTML pages need GA4 script added manually
285 | Analytics & Tracking | Rank Math Analytics — connect to GSC for keyword rank tracking in WP | High | Pending
286 | Analytics & Tracking | Conversion tracking — WhatsApp click, contact form, call click events in GA4 | High | Pending | Primary KPI = daily calls
287 | Analytics & Tracking | Monthly SEO report — rankings, traffic, GMB views, calls, conversions | Medium | Pending | Baseline at 30 days post-GMB setup
288 | Analytics & Tracking | Set up Google Alerts for 'Vardhini Vastu' and 'Raghavendra Hebbur' | Medium | Pending | Brand monitoring — see who is mentioning you
289 | Analytics & Tracking | SEMrush weekly alerts — keyword changes, backlink gains/losses | High | Pending
Daily Conversion Engine
290 | Daily Conversion Engine | WhatsApp Business — set up auto-reply with consultation booking info | High | Pending | Every page has +91 97391 05574 — ensure WhatsApp Business is configured
291 | Daily Conversion Engine | Click-to-call tracking — ensure all phone numbers are tap-to-call on mobile | High | Pending | tel: links on all pages
292 | Daily Conversion Engine | Response time target: reply to all inquiries within 2 hours | High | Pending | Speed of response = conversion rate
293 | Daily Conversion Engine | Calendly or booking link on every page — reduce friction | High | Pending | Every page CTA should link to a direct booking page
294 | Daily Conversion Engine | GMB: Missed call auto-text — enable if available in your region | Medium | Pending
295 | Daily Conversion Engine | Retargeting pixel (Google/Meta) — track visitors, run retargeting ads | Medium | Pending | Visitors who don't convert get retargeted with consultation offer
296 | Daily Conversion Engine | Offer: Free 15-min vastu Q&A call — funnel to paid consultation | High | Pending | Low-friction entry offer increases contact rate
297 | Daily Conversion Engine | Review funnel: after every consultation, send WhatsApp review request | High | Pending | Systematise reviews — every happy client = 1 GMB review
298 | Daily Conversion Engine | Daily check: GSC clicks, GA4 sessions, WhatsApp messages, GMB calls | High | Pending | 30-min daily review of key metrics to stay on top of momentum

## Bangalore Locality Pipeline
Bangalore Locality Pipeline — 50 Localities Total
20 Live + 30 Extended (South/Kanakapura ¦ East/Hoskote ¦ North/Devanahalli ¦ West/Tumkur Road)
# | Slug | Corridor | Status | Notes
1 | vastu-consultant-whitefield | Core — East | Done | WP Live
2 | vastu-consultant-indiranagar | Core — Central | Done | WP Live
3 | vastu-consultant-koramangala | Core — South | Done | WP Live
4 | vastu-consultant-hsr-layout | Core — South | Done | WP Live
5 | vastu-consultant-electronic-city | Core — South | Done | WP Live
6 | vastu-consultant-jp-nagar | Core — South | Done | WP Live
7 | vastu-consultant-jayanagar | Core — South | Done | WP Live
8 | vastu-consultant-bannerghatta-road | Core — South | Done | WP ID 267
9 | vastu-consultant-sarjapur-road | Core — East | Done | WP ID 268
10 | vastu-consultant-marathahalli | Core — East | Done | WP ID 269
11 | vastu-consultant-yelahanka | Core — North | Done | WP ID 270
12 | vastu-consultant-hebbal | Core — North | Done | WP ID 271
13 | vastu-consultant-rajajinagar | Core — West | Done | WP ID 272
14 | vastu-consultant-malleswaram | Core — West | Done | WP ID 273
15 | vastu-consultant-basavanagudi | Core — South | Done | WP ID 274
16 | vastu-consultant-btm-layout | Core — South | Done | WP ID 275
17 | vastu-consultant-banaswadi | Core — East | Done | WP ID 276
18 | vastu-consultant-bellandur | Core — East | Done | WP ID 277
19 | vastu-consultant-kr-puram | Core — East | Done | WP ID 278
20 | vastu-consultant-nagarbhavi | Core — West | Done | WP ID 279
21 | vastu-consultant-banashankari | South / Kanakapura | Pending | Dense residential
22 | vastu-consultant-uttarahalli | South / Kanakapura | Pending
23 | vastu-consultant-kengeri | South / Mysore Road | Pending
24 | vastu-consultant-rajarajeshwari-nagar | South / Mysore Road | Pending | RR Nagar — fast growth
25 | vastu-consultant-gottigere | South / Bannerghatta Rd | Pending
26 | vastu-consultant-hulimavu | South / Bannerghatta Rd | Pending
27 | vastu-consultant-kanakapura-road | South / Kanakapura | Pending | NICE Road corridor
28 | vastu-consultant-subramanyapura | South / Kanakapura | Pending
29 | vastu-consultant-konanakunte | South / Kanakapura | Pending
30 | vastu-consultant-mysore-road | South / Mysore Road | Pending | Full corridor page
31 | vastu-consultant-bidadi | South / Mysore Road | Pending | Satellite town — Toyota
32 | vastu-consultant-ramanagara | South / Mysore Road | Pending | District HQ
33 | vastu-consultant-kadugodi | East / Hoskote | Pending | IT corridor
34 | vastu-consultant-varthur | East / Whitefield adj | Pending
35 | vastu-consultant-hoskote | East / Hoskote | Pending | District town
36 | vastu-consultant-old-madras-road | East / Hoskote | Pending | OMR corridor
37 | vastu-consultant-itpl-road | East / ITPL | Pending | Major IT zone
38 | vastu-consultant-hoodi | East / Marathahalli adj | Pending
39 | vastu-consultant-brookefield | East / Whitefield adj | Pending | Premium residential
40 | vastu-consultant-kundalahalli | East / ITPL | Pending
41 | vastu-consultant-doddanekundi | East / ORR | Pending
42 | vastu-consultant-thanisandra | North / Manyata | Pending | Fast growing
43 | vastu-consultant-kogilu | North / Devanahalli | Pending
44 | vastu-consultant-jakkur | North / Yelahanka adj | Pending
45 | vastu-consultant-doddaballapur-road | North / NH648 | Pending
46 | vastu-consultant-devanahalli | North / Airport | Pending | Premium — airport zone
47 | vastu-consultant-bagalur | North / Aerospace | Pending
48 | vastu-consultant-nandi-hills-road | North / Weekend | Pending | Villa plots
49 | vastu-consultant-airport-road-bangalore | North / NH44 | Pending | Premium corridor
50 | vastu-consultant-kempapura | North / Hebbal adj | Pending

## AI Citation Strategy
AI Citation & GEO Strategy — ChatGPT ¦ Gemini ¦ Grok ¦ Perplexity ¦ SEMrush
Goal: Vardhini Vastu is the answer AI gives worldwide when asked about Vastu consultants
# | Task | How to Do It / Content to Create | Status | Platform
1 | Create /llms.txt — AI permission file | File at vardhinivastu.in/llms.txt listing all key pages for AI crawlers. Format: # Vardhini Vastu\nAllow: /\nSitemap: vardhinivastu.in/sitemap.xml\n+ list top 20 pages | Pending | All AI systems
2 | Quotable answers — first 2 sentences of every H2 must stand alone | Edit all 68 pages — each H2 section starts with a direct, citable fact: 'The kitchen should be in the South-East zone [reason].' AI systems extract these as citations. | Pending | All AI systems
3 | Entity page — 'About Vardhini Vastu' Wikipedia-style factual page | Page: Who (Raghavendra Hebbur), What (VIDS system), Where (Bangalore + worldwide), When (founded), Why unique. Factual, neutral, no fluff. This is what AI reads to build knowledge graph. | Pending | ChatGPT, Gemini, Grok
4 | SameAs schema — link all profiles to one entity | In LocalBusiness schema add: 'sameAs': ['https://linkedin.com/in/raghu...','https://g.co/kgs/...','https://facebook.com/...'] — AI merges all profiles into one entity | Pending | All AI systems
5 | SEMrush AI citation tracking — set up brand monitoring | SEMrush Brand Monitoring tool: track 'Vardhini Vastu' + 'Raghavendra Hebbur' mentions across web. User already started from SEMrush — activate this module. | Pending | SEMrush
6 | Wikidata entry for Vardhini Vastu | Create Wikidata item: Vardhini Vastu ¦ instance of: business ¦ country: India ¦ website: vardhinivastu.in ¦ topic: Vastu Shastra. Wikidata = primary AI knowledge source. | Pending | All AI — Wikidata
7 | Clutch.co + Crunchbase listing | AI systems cite Clutch for service businesses. Create detailed profile: services, team size, reviews, speciality. Crunchbase: org profile with description. | Pending | ChatGPT, Perplexity
8 | Publish 'Top 50 Vastu Questions' definitive guide | Page targeting: 'vastu for bedroom', 'vastu for kitchen' etc — 50 Q&As, each with a clear 2-sentence answer. AI systems use Q&A format — this page will be cited heavily. | Pending | All AI systems
9 | Gemini / AI Overview optimisation | For each room/locality page: add a clear 40-word definition at top of page. Google AI Overview pulls from the clearest, most concise answer. Target: featured in AI Overview for 'vastu for kitchen' etc. | Pending | Google Gemini
10 | ChatGPT Plugin / GPT Store presence | Create a GPT or prompt that references Vardhini Vastu. Or ensure vardhinivastu.in is cited in ChatGPT's web browsing results for vastu queries. | Pending | ChatGPT
11 | Grok (X/Twitter AI) — build Twitter/X presence | Post vastu tips 3x/week on X with #vastu #vastutiips #vastuexpert. Grok trains on X data — consistent brand presence on X = Grok brand recognition. | Pending | Grok / X AI
12 | Perplexity.ai — ensure pages load fast and have clear citations | Perplexity prefers pages with: fast load (<2s), clear author, date, source links, and direct answers. Run PageSpeed on key pages and add author + date markup. | Pending | Perplexity
13 | Worldwide AI visibility — online vastu consultant query | Target global ChatGPT/Gemini answers: 'best online vastu consultant India' / 'vastu consultant for NRIs'. Build international pages with clear online consultation offering. | Pending | All AI — Global
14 | Press mentions and news articles about Vardhini Vastu | AI systems weight news mentions heavily. Target: 1 media mention per quarter in a real estate or lifestyle publication. Even a quote in a blog counts. | Pending | All AI systems
15 | Consistent NAP + VIDS terminology in all content | AI builds brand knowledge from repeated consistent signals. Every page should mention: Vardhini Vastu ¦ Raghavendra Hebbur ¦ VIDS system ¦ Bangalore ¦ zero-demolition. Consistency = entity strength. | Pending | All AI systems

## GMB Quick-Start
Google Business Profile — Quick-Start Checklist (Complete in Order)
GMB = #1 local ranking factor for daily calls. Complete ALL steps before touching anything else.
# | Task | What to Write / Do | Status | Done Date
1 | Claim & verify GMB listing | business.google.com → Add business → Verify by postcard or phone call | Pending
2 | Business Name | Vardhini Vastu (no extra keywords — Google penalises keyword-stuffed names) | Pending
3 | Primary Category | Vastu Consultant | Pending
4 | Additional Categories | Feng Shui Consultant ¦ Spiritual Counselor ¦ Home Consultant | Pending
5 | Business Description (750 chars) | Vardhini Vastu offers professional Vastu Shastra consultancy by Raghavendra Hebbur in Bangalore. Specialising in the VIDS system (Vardhini Integrated Direction System) — a 16-zone degree-accurate Vastu analysis with zero-demolition corrections. Services include residential vastu, commercial vastu, plot analysis, and online consultations across India and worldwide. | Pending
6 | Phone Number | +91 97391 05574 (must match website and all citations exactly — NAP consistency) | Pending
7 | Website URL | https://vardhinivastu.in | Pending
8 | Address / Service Area | Full Bangalore address OR hide address + set service area. Add all 50 localities. | Pending
9 | Opening Hours | Mon-Sat 10am-7pm ¦ Sun By Appointment (accurate hours = higher call rate) | Pending
10 | Services — add each | 1) Residential Vastu 2) Commercial Vastu 3) Online Consultation 4) Plot/Land Vastu 5) VIDS Analysis | Pending
11 | Booking / Appointment Link | https://vardhinivastu.in/vastu-consultant-bangalore-contact/ | Pending
12 | Cover Photo | Professional headshot of Raghavendra Hebbur or clean vastu compass image (1332x750px) | Pending
13 | Logo | Vardhini Vastu logo (250x250px minimum, square) | Pending
14 | Work Photos (8-10) | Consultation session, vastu charts, before/after home layouts, compass analysis | Pending
15 | Q&A — pre-populate 10 questions | Add: What is VIDS? / Do you do online vastu? / Areas served? / Cost? / No demolition? | Pending
16 | Enable Messaging | Turn on GMB messaging — mention WhatsApp +91 97391 05574 in auto-reply | Pending
17 | First GMB Post | Post: '5 Signs Your Home Needs a Vastu Check' — link to /vastu-for-bedroom | Pending
18 | Request first 5-10 reviews | WhatsApp past clients: 'Could you leave a quick Google review? [GMB link]' | Pending
19 | Respond to ALL reviews within 24h | Positive: thank + mention VIDS. Negative: acknowledge + offer offline resolution | Pending
20 | Weekly GMB post schedule | Every Monday: vastu tip. Every Thursday: client success or educational. Rotate topics. | Pending

## Content Calendar
Content Calendar — Google News + RSS + Blog + GMB Posts
2 blog posts/week = Google News eligibility. 1 GMB post/week = map rank boost. All feed RSS.
# | Content Type | Title / Topic | Platform | Status | Notes | Publish Date
1 | Blog Post | 5 Vastu Mistakes in Bangalore Apartments That Cost You Peace | Blog + Google News + RSS | Pending | High local intent — link to room pages
2 | GMB Post | Vastu Tip: Why your refrigerator should never be in the NE corner | GMB | Pending | Link to /vastu-for-kitchen
3 | Blog Post | Vastu for 2BHK Apartments: Room-by-Room Guide | Blog + Google News | Pending | Link to bedroom, kitchen, bathroom pages
4 | GMB Post | Client Result: Corrected master bedroom zone — better sleep in 7 days | GMB | Pending | Social proof post
5 | Blog Post | South-Facing House Vastu: Why It Is Not Inauspicious (The Truth) | Blog + Google News | Pending | High volume search — controversial angle = shares
6 | GMB Post | Vastu for home office — Work from home Vastu tips | GMB | Pending | Link to /vastu-for-study-room
7 | Blog Post | VIDS System Explained: How 16-Zone Vastu Analysis Works | Blog + Google News | Pending | Differentiator content — brand building
8 | GMB Post | Now serving all Whitefield and Sarjapur Road apartments — book a consultation | GMB | Pending | Locality targeting
9 | Blog Post | Vastu Before Buying a Flat: 10 Things to Check | Blog + Google News | Pending | Apartment buyer intent — link to apartment pages
10 | GMB Post | Vastu for Pooja Room: NE is the sacred zone for maximum divine grace | GMB | Pending | Link to /vastu-for-pooja-room
11 | Blog Post | Vastu for IT Professionals in Bangalore: Office and Home Alignment | Blog + Google News | Pending | IT corridor targeting
12 | GMB Post | Online Vastu Consultations Available Worldwide — Book via WhatsApp | GMB | Pending | International + online offer
13 | Blog Post | Vastu for Factory and Industrial Spaces: Zone Rules for Productivity | Blog + Google News | Pending | Industrial segment — new revenue stream
14 | GMB Post | Vastu Tip: The one correction that improves sleep immediately | GMB | Pending | Head direction — bedroom page link
15 | Blog Post | Vardhini Vastu Case Study: Zero-Demolition Correction in Whitefield Apartment | Blog + Google News | Pending | E-E-A-T and social proof
16 | Quora Answer | Answered: Best vastu consultant in Bangalore? | Quora + Off-page | Pending | 2 answers/week — link to site
17 | Blog Post | Vastu for Devanahalli and Airport Road Homes: Luxury Zone Guide | Blog + Google News | Pending | New locality targeting
18 | X/Twitter Post | Thread: 7 vastu rules for the bedroom [with images] | X/Twitter + Grok | Pending | 3 posts/week for Grok AI training
19 | Blog Post | Vastu for NRIs: How to Check Vastu of Your India Home Remotely | Blog + Google News | Pending | International + online consultation
20 | GMB Post | Now covering Devanahalli, Airport Road, and Hebbal — call to book | GMB | Pending | Extended north Bangalore locality push