## Dashboard
Vardhini Vastu — SEO Master Tracker v2
vardhinivastu.in & vardhinivastu.com ¦ Raghavendra Hebbur ¦ Updated: 19 May 2026
Metric | Count | % Total | Notes
Total Tasks | 298 | 100% | Across all 26 categories
Done | 92 | 24% | Live on site / process complete
Pending | 204 | 76% | Not yet started — prioritise by colour
In Progress | 0 | — | Currently active
Pages Live on WP | 68 | — | Rooms 25 + Localities 20 + Cities 15 + International 8
Bangalore Localities Total | 50 | — | 20 live + 30 extended (South/East/North/West corridors)
Apartment Pages Pipeline | 24 | — | Bangalore 14 + Cities 10 — no builder names
Industrial Area Pages | 23 | — | Bangalore 10 + India 13 — commercial vastu segment
GMB Tasks (Highest Priority) | 18 | — | Zero started — #1 lever for daily calls
AI Citation Tasks | 15 | — | ChatGPT, Gemini, Grok, Perplexity, SEMrush
TOP PRIORITY ACTIONS (start here)
# | Action | Category | Why It Matters
1 | Claim & complete Google Business Profile | GMB & Local SEO | Direct calls = revenue
2 | Add vardhinivastu.com footer to all .in pages | Footer & Templates | Ranked .com in 24hrs
3 | Set Rank Math meta on all 68 live pages | Strategy & Competitors | Quick SEO wins
4 | Create llms.txt — AI citation foundation | AI Citation & GEO | ChatGPT/Gemini/Grok
5 | Submit XML sitemap + verify GSC | Technical SEO | Index all new pages
6 | Build 30 extended Bangalore locality pages | Bangalore Extended | Dominate micro-searches
7 | Apartment targeting pages (2BHK/3BHK etc) | Apartment Targeting - Blore | High intent buyers
8 | Industrial area pages — factory/warehouse vastu | Industrial Areas - Bangalore | Commercial revenue
9 | Weekly GMB posts + review collection | GMB & Local SEO | Map pack ranking
10 | Google News setup + 2 posts/week | Google News & RSS | First page news results
SESSION COMPLETED ─ 16 May 2026
| Action | Category | Result | Notes
| XML Sitemap resubmitted | Technical SEO | ✅ Done | sitemap_index.xml + sitemap.xml → 206 URLs queued in GSC
| robots.txt audited | Technical SEO | ✅ Done | All pages crawlable, AI bots whitelisted
| llms.txt created | AI / GEO | ✅ Done | 130+ pages listed for ChatGPT, Perplexity, Claude, Gemini
| GSC FAQ schema fix submitted | Schema / GSC | ✅ Validate Fix clicked | Duplicate FAQPage error — HTML microdata removed, JSON-LD kept
| GSC Review snippets fix submitted | Schema / GSC | ✅ Validate Fix clicked | Missing itemReviewed fixed on all 3 review blockquotes
| Priority indexing — Homepage | GSC Indexing | ✅ Requested | Added to Google priority crawl queue
| Priority indexing — Whitefield | GSC Indexing | ✅ Requested
| Priority indexing — Koramangala | GSC Indexing | ✅ Requested
| Priority indexing — HSR Layout | GSC Indexing | ✅ Requested
| Priority indexing — Electronic City | GSC Indexing | ✅ Requested
| Priority indexing — JP Nagar | GSC Indexing | ✅ Requested
IN PROGRESS ─ User Action Required
| Action | Category | Status | Next Step
| Rank Math 90+ fix on homepage | On-Page SEO | 🔄 User fixing now | Apply blueprint: title format, H2 rule, keyword density, external link
| Social profiles fix | Schema / Social | ⏳ Needs clarification | Confirm: broken links on site? Bad OG preview? Wrong sameAs in schema?
| GSC FAQ validation | Schema / GSC | 🔄 Google crawling | Wait 2–5 days for Google to re-crawl and confirm fix
| GSC Review snippets validation | Schema / GSC | 🔄 Google crawling | Wait 2–5 days. Expected: 0 errors after crawl
| Sitemap crawl — 206 pages | GSC Indexing | 🔄 Google queued | Google will discover all 206 pages from sitemap in next 1–2 weeks
NEXT PRIORITY ACTIONS (after Rank Math fix)
| Priority | Action | Category | Why It Matters
| #1 — TODAY | Claim & complete Google Business Profile (GBP) | GMB & Local SEO | Single biggest lever for calls. Zero cost. business.google.com
| #2 — TODAY | Fix social profiles issue (clarify type first) | Schema / Social | Broken sameAs links = missed E-E-A-T signal + poor social sharing
| #3 — THIS WEEK | Add internal links: homepage → top 10 locality pages | Technical SEO | Google finds pages via internal links, not just sitemap
| #4 — THIS WEEK | Core pages: About (E-E-A-T), Contact (schema+Maps), Services | Core Pages | Named expert page = E-E-A-T boost for entire domain
| #5 — THIS WEEK | Footer with NAP on all standalone HTML pages (vv-blank.php) | Footer / Templates | One template change covers all 43 standalone pages instantly
| #6 — THIS WEEK | WhatsApp Business — configure auto-reply with booking info | Conversion | All pages show +91 97391 05574 — ensure WA Business is live
| #7 — NEXT WEEK | Launch blog: 2 cornerstone posts for Google News eligibility | Content / News | Feeds RSS, builds internal links, AI citation target
| #8 — NEXT WEEK | Citations Tier 1: Justdial, Sulekha, UrbanClap, IndiaMart | Off-Page / Local | NAP consistency + local authority signals for map pack
| #9 — NEXT WEEK | GA4 conversion tracking: WhatsApp click, call click events | Analytics | Cannot optimise what you cannot measure
| #10 — ONGOING | GMB weekly posts + respond to all reviews within 24hrs | GMB & Local SEO | Review velocity + GMB activity = map pack ranking boost
| SESSION 2 COMPLETED ─ 16 May 2026 | Action | Category | Result
|  | Internal links: 14 locality pills linked on homepage | Technical SEO | ✅ Done
|  | Footer NAP: vv-blank.php already serving 120 pages | Footer & Templates | ✅ Confirmed Done
|  | LocalBusiness schema: injected into vv-blank.php footer | Schema / SEO | ✅ Done — all 120 standalone pages
|  | LocalBusiness schema: wp_footer hook in functions.php | Schema / SEO | ✅ Done — all 86 WP-theme pages
|  | SSL mixed content: HTTP link fixed on homepage | Technical SEO | ✅ Done — 1 HTTP img → HTTPS
|  | Area pill links: CSS hover style for anchors added | Technical SEO | ✅ Done
|  | TOC removed: About, Contact, Services pages | Core Pages | ✅ Done (last session)
|  | About page: Amazon KDP book showcase added | Core Pages / E-E-A-T | ✅ Done (last session)

## Master Task List
# | Category | Task / Page | Priority | Status | Notes / URL | Target Date | Done Date
Strategy & Competitors
1 | Strategy & Competitors | Identify top 5 Vastu consultants competing in Bangalore | High | Done | Competitors mapped: Mystic Space, VastuPlus, Vastu Devayah Namah, Astro Vastu, local listings
2 | Strategy & Competitors | Map competitor keyword universe — locality, city, room, direction pages | High | Done | Full roadmap benchmarked
3 | Strategy & Competitors | SEO content roadmap: Rooms + Localities + Cities + International + Edu + Directions | High | Done | 68+ pages planned and executed
4 | Strategy & Competitors | Rank Math 90+ blueprint documented | High | Done | In memory/feedback_rankmath_blueprint.md
5 | Strategy & Competitors | Set Rank Math focus KW + SEO title + meta desc on all 68 live pages | High | Pending | Each page has metadata in HTML comment — paste into Rank Math for every page
6 | Strategy & Competitors | Monthly keyword rank tracking — top 30 target keywords | Medium | Pending | GSC + Rank Math rank tracker
7 | Strategy & Competitors | Competitor backlink gap analysis | Medium | Pending | Run /seo backlinks against top 3 competitors
8 | Strategy & Competitors | SEMrush project setup — track domain, backlinks, position changes | High | Pending | User started from SEMrush — ensure project is live and alerts set
Technical SEO
9 | Technical SEO | vv-blank.php custom template — created and verified | High | Done | Serves standalone HTML pages without Astra theme wrapper
10 | Technical SEO | WP permalink /%postname%/ — confirmed clean URLs on all pages | High | Done
11 | Technical SEO | XML sitemap — verify includes all 68+ new pages, submit to GSC | High | Done | Sitemap resubmitted 16/05 with 206 URLs (sitemap.xml + sitemap_index.xml) |  | 16/05/2026
12 | Technical SEO | robots.txt — no important locality/room pages blocked | High | Done | robots.txt audited clean - all locality/room pages allowed, AI bots allowed |  | 16/05/2026
13 | Technical SEO | SSL/HTTPS — verify no mixed content on any page | High | Done |  | 16 May 2026
14 | Technical SEO | Core Web Vitals (LCP, CLS, INP) — baseline via PageSpeed Insights | High | Pending | Run on homepage + 3 locality pages
15 | Technical SEO | Mobile rendering — all pages correct on mobile | High | Pending | Test standalone HTML pages vs fragment pages in Astra
16 | Technical SEO | Canonical tags — no duplicate content across city/locality variations | Medium | Pending | Check Rank Math canonical on all pages
17 | Technical SEO | Internal linking — rooms to localities, localities to cities, all to CTA | Medium | Done | Build cross-link structure throughout site | 16 May 2026
18 | Technical SEO | Image upload — upload actual WebP images for all 68 page placeholder img tags | Medium | Pending | Pages reference /wp-content/uploads/ paths — images not yet uploaded
19 | Technical SEO | 404 audit after indexing — fix any broken internal links | Low | Done | Use GSC Coverage report or Screaming Frog |  | 19/05/2026
20 | Technical SEO | Schema markup validation — all JSON-LD in room and locality pages passes | High | In Progress | FAQ duplicate fixed + Review itemReviewed fixed. GSC Validate Fix clicked 16/05 |  | 16/05/2026
21 | Technical SEO | hreflang — add en-IN and en tags for Indian audience clarity | Low | Pending
Site Parity .com vs .in
22 | Site Parity .com vs .in | Audit vardhinivastu.com — map all pages that exist there vs .in | High | Done | Social profiles issue resolved by user 16/05 |  | 16/05/2026
23 | Site Parity .com vs .in | Replicate all high-performing .com pages onto .in | High | Pending | The .com ranks well — port its best content to .in
24 | Site Parity .com vs .in | 301 redirect strategy — decide if .in should eventually replace .com or coexist | High | Pending | Consider canonical cross-domain strategy or full migration
25 | Site Parity .com vs .in | Ensure homepage on .in has equal or better SEO treatment than .com | High | Pending | Title, meta, H1, schema, CTA all need to match or exceed .com
26 | Site Parity .com vs .in | Ensure contact/booking page on .in matches .com | High | Pending | Conversion page parity is critical for daily calls
27 | Site Parity .com vs .in | Ensure testimonials/reviews on .in match .com | Medium | Pending | Social proof is an E-E-A-T signal — both domains need it
28 | Site Parity .com vs .in | Cross-link .com and .in strategically to build combined authority | Medium | Pending | Link from .com blog posts to .in service pages and vice versa
29 | Site Parity .com vs .in | Verify GSC has both domains verified and tracked separately | High | Pending | Monitor both .in and .com in GSC separately
Footer & Templates
30 | Footer & Templates | Add vardhinivastu.com footer to ALL vardhinivastu.in pages — it ranked .com in 24hrs | High | Done | Footer contains key internal links, NAP, and trust signals — replicate exactly on .in | 16 May 2026
31 | Footer & Templates | Create global footer include — one place to update, applies to all pages | High | Done | Either a WP template part or a PHP include in vv-blank.php for standalone pages | 16 May 2026
32 | Footer & Templates | Footer content: NAP, service links, locality links, city links, social, schema | High | Done | NAP: Vardhini Vastu ¦ Bangalore ¦ +91 97391 05574 ¦ vardhinivastu.in | 16 May 2026
33 | Footer & Templates | Add footer to all 25 residential room pages | High | Done | Fragment pages need footer injected or appended | 16 May 2026
34 | Footer & Templates | Add footer to all 20 Bangalore locality pages | High | Done | Standalone HTML pages — footer needs to be in the HTML file | 16 May 2026
35 | Footer & Templates | Add footer to all 15 Indian city pages | High | Done |  | 16 May 2026
36 | Footer & Templates | Add footer to all 8 international pages | High | Done |  | 16 May 2026
37 | Footer & Templates | Update vv-blank.php to auto-inject footer on all standalone HTML pages | High | Done | One template change covers all 43 standalone pages at once | 16 May 2026
Residential Rooms (25)
38 | Residential Rooms (25) | vastu-for-kitchen (WP ID 283) | High | Done | vardhinivastu.in/vastu-for-kitchen
39 | Residential Rooms (25) | vastu-for-bedroom (WP ID 284) | High | Done | vardhinivastu.in/vastu-for-bedroom
40 | Residential Rooms (25) | vastu-for-living-room (WP ID 285) | High | Done
41 | Residential Rooms (25) | vastu-for-dining-room (WP ID 286) | High | Done
42 | Residential Rooms (25) | vastu-for-bathroom (WP ID 287) | High | Done
43 | Residential Rooms (25) | vastu-for-pooja-room (WP ID 288) | High | Done
44 | Residential Rooms (25) | vastu-for-main-entrance (WP ID 289) | High | Done
45 | Residential Rooms (25) | vastu-for-study-room (WP ID 290) | High | Done
46 | Residential Rooms (25) | vastu-for-guest-room (WP ID 291) | Medium | Done
47 | Residential Rooms (25) | vastu-for-childrens-room (WP ID 292) | High | Done
48 | Residential Rooms (25) | vastu-for-master-bedroom (WP ID 293) | High | Done
49 | Residential Rooms (25) | vastu-for-mandir-at-home (WP ID 294) | High | Done
50 | Residential Rooms (25) | vastu-for-balcony (WP ID 295) | Medium | Done
51 | Residential Rooms (25) | vastu-for-mirrors (WP ID 296) | Medium | Done
52 | Residential Rooms (25) | vastu-for-shoe-rack (WP ID 297) | Low | Done
53 | Residential Rooms (25) | vastu-for-staircase (WP ID 298) | Medium | Done
54 | Residential Rooms (25) | vastu-for-basement (WP ID 299) | Medium | Done
55 | Residential Rooms (25) | vastu-for-car-parking (WP ID 300) | Medium | Done
56 | Residential Rooms (25) | vastu-for-garden (WP ID 301) | Medium | Done
57 | Residential Rooms (25) | vastu-for-water-tank (WP ID 302) | Medium | Done
58 | Residential Rooms (25) | vastu-for-swimming-pool (WP ID 303) | Low | Done
59 | Residential Rooms (25) | vastu-for-septic-tank (WP ID 304) | Low | Done
60 | Residential Rooms (25) | vastu-for-wall-clock (WP ID 305) | Low | Done
61 | Residential Rooms (25) | vastu-for-colors (WP ID 306) | High | Done
62 | Residential Rooms (25) | vastu-for-toilet (WP ID 307) | Medium | Done
Bangalore Core Localities
63 | Bangalore Core Localities | vastu-consultant-whitefield | High | Done | Live ¦ GSC priority indexing requested 16/05
64 | Bangalore Core Localities | vastu-consultant-indiranagar | High | Done | Live
65 | Bangalore Core Localities | vastu-consultant-koramangala | High | Done | Live ¦ GSC priority indexing requested 16/05
66 | Bangalore Core Localities | vastu-consultant-hsr-layout | High | Done | Live ¦ GSC priority indexing requested 16/05
67 | Bangalore Core Localities | vastu-consultant-electronic-city | High | Done | Live ¦ GSC priority indexing requested 16/05
68 | Bangalore Core Localities | vastu-consultant-jp-nagar | High | Done | Live ¦ GSC priority indexing requested 16/05
69 | Bangalore Core Localities | vastu-consultant-jayanagar | High | Done | Live
70 | Bangalore Core Localities | vastu-consultant-bannerghatta-road | Medium | Done | WP ID 267
71 | Bangalore Core Localities | vastu-consultant-sarjapur-road | Medium | Done | WP ID 268
72 | Bangalore Core Localities | vastu-consultant-marathahalli | Medium | Done | WP ID 269
73 | Bangalore Core Localities | vastu-consultant-yelahanka | Medium | Done | WP ID 270
74 | Bangalore Core Localities | vastu-consultant-hebbal | Medium | Done | WP ID 271
75 | Bangalore Core Localities | vastu-consultant-rajajinagar | Medium | Done | WP ID 272
76 | Bangalore Core Localities | vastu-consultant-malleswaram | Medium | Done | WP ID 273
77 | Bangalore Core Localities | vastu-consultant-basavanagudi | Medium | Done | WP ID 274
78 | Bangalore Core Localities | vastu-consultant-btm-layout | Medium | Done | WP ID 275
79 | Bangalore Core Localities | vastu-consultant-banaswadi | Low | Done | WP ID 276
80 | Bangalore Core Localities | vastu-consultant-bellandur | Medium | Done | WP ID 277
81 | Bangalore Core Localities | vastu-consultant-kr-puram | Low | Done | WP ID 278
82 | Bangalore Core Localities | vastu-consultant-nagarbhavi | Low | Done | WP ID 279
Bangalore Extended - South
83 | Bangalore Extended - South | vastu-consultant-banashankari | High | Pending | Dense residential — near Jayanagar, high apartment density
84 | Bangalore Extended - South | vastu-consultant-uttarahalli | Medium | Pending | Growing residential suburb south of Banashankari
85 | Bangalore Extended - South | vastu-consultant-kengeri | Medium | Pending | West Bangalore — affordable housing corridor
86 | Bangalore Extended - South | vastu-consultant-rajarajeshwari-nagar | High | Pending | RR Nagar — one of Bangalore's fastest growing suburbs
87 | Bangalore Extended - South | vastu-consultant-gottigere | Medium | Pending | South Bangalore — near Bannerghatta Road
88 | Bangalore Extended - South | vastu-consultant-hulimavu | Medium | Pending | Between BTM and Bannerghatta Road
89 | Bangalore Extended - South | vastu-consultant-kanakapura-road | High | Pending | Major growth corridor — luxury apartments, NICE Road
90 | Bangalore Extended - South | vastu-consultant-bidadi | Medium | Pending | Satellite town on Mysore Road — Toyota plant area, industrial + residential
91 | Bangalore Extended - South | vastu-consultant-ramanagara | Medium | Pending | District HQ — Silk City — growing real estate
92 | Bangalore Extended - South | vastu-consultant-mysore-road | High | Pending | Entire Mysore Road corridor — Kengeri to Bidadi
93 | Bangalore Extended - South | vastu-consultant-subramanyapura | Low | Pending | Residential pocket near Kanakapura Road
94 | Bangalore Extended - South | vastu-consultant-konanakunte | Low | Pending | Near NICE Road junction
Bangalore Extended - East
95 | Bangalore Extended - East | vastu-consultant-kadugodi | High | Pending | Between Whitefield and Hoskote — IT / apartment corridor
96 | Bangalore Extended - East | vastu-consultant-varthur | High | Pending | Next to Whitefield — rapid apartment development
97 | Bangalore Extended - East | vastu-consultant-hoskote | High | Pending | District town east of Bangalore — industrial + residential growth
98 | Bangalore Extended - East | vastu-consultant-old-madras-road | Medium | Pending | OMR corridor — KR Puram to Hoskote
99 | Bangalore Extended - East | vastu-consultant-itpl-road | High | Pending | ITPL / Hoodi — major IT zone, high apartment density
100 | Bangalore Extended - East | vastu-consultant-hoodi | Medium | Pending | Between Marathahalli and Whitefield
101 | Bangalore Extended - East | vastu-consultant-brookefield | Medium | Pending | Premium residential near Whitefield
102 | Bangalore Extended - East | vastu-consultant-kundalahalli | Low | Pending | Near ITPL
103 | Bangalore Extended - East | vastu-consultant-doddanekundi | Low | Pending | Outer Ring Road — Marathahalli to Whitefield
Bangalore Extended - North
104 | Bangalore Extended - North | vastu-consultant-thanisandra | High | Pending | Fast growing north Bangalore — Manyata Tech Park area
105 | Bangalore Extended - North | vastu-consultant-kogilu | Medium | Pending | North of Hebbal — new residential development
106 | Bangalore Extended - North | vastu-consultant-jakkur | Medium | Pending | Near Yelahanka — residential + weekend homes
107 | Bangalore Extended - North | vastu-consultant-doddaballapur-road | Medium | Pending | NH-648 corridor — industrial and residential mix
108 | Bangalore Extended - North | vastu-consultant-devanahalli | High | Pending | Near Kempegowda International Airport — luxury villas, ITIR zone
109 | Bangalore Extended - North | vastu-consultant-bagalur | Medium | Pending | Aerospace park zone — emerging residential
110 | Bangalore Extended - North | vastu-consultant-nandi-hills-road | Low | Pending | Weekend home corridor — villa plots
111 | Bangalore Extended - North | vastu-consultant-airport-road-bangalore | High | Pending | NH-44 corridor — premium residential + commercial
112 | Bangalore Extended - North | vastu-consultant-kempapura | Low | Pending | Near Hebbal — residential pocket
Bangalore Extended - West/NW
113 | Bangalore Extended - West/NW | vastu-consultant-yeshwanthpur | High | Pending | Major Tumkur Road junction — dense commercial + residential
114 | Bangalore Extended - West/NW | vastu-consultant-peenya | High | Pending | Largest industrial estate in South Asia — commercial vastu opportunity
115 | Bangalore Extended - West/NW | vastu-consultant-dasarahalli | Medium | Pending | Industrial + residential on Tumkur Road
116 | Bangalore Extended - West/NW | vastu-consultant-jalahalli | Medium | Pending | Air Force Station area — residential
117 | Bangalore Extended - West/NW | vastu-consultant-mathikere | Medium | Pending | West Bangalore residential
118 | Bangalore Extended - West/NW | vastu-consultant-tumkur-road | High | Pending | Full NH-48 corridor page — Yeshwanthpur to Nelamangala
119 | Bangalore Extended - West/NW | vastu-consultant-nelamangala | Medium | Pending | Logistics hub town — warehouse + residential
120 | Bangalore Extended - West/NW | vastu-consultant-magadi-road | Medium | Pending | West Bangalore corridor
121 | Bangalore Extended - West/NW | vastu-consultant-vijayanagar | High | Pending | Dense residential — one of Bangalore's oldest planned areas
122 | Bangalore Extended - West/NW | vastu-consultant-tumkur | Medium | Pending | Tumkur city — district HQ, growing real estate
Apartment Targeting - Blore
123 | Apartment Targeting - Blore | vastu-for-high-rise-apartments-bangalore | High | Pending | Target buyers of 15+ floor apartments in Whitefield, Hebbal, Sarjapur — no builder names
124 | Apartment Targeting - Blore | vastu-for-2bhk-apartment-bangalore | High | Pending | Biggest search segment — 2BHK vastu rules specific to compact apartments
125 | Apartment Targeting - Blore | vastu-for-3bhk-apartment-bangalore | High | Pending | 3BHK buyers — SW master bedroom in apartment context
126 | Apartment Targeting - Blore | vastu-for-studio-apartment-bangalore | Medium | Pending | Studio/1BHK — young IT professionals target audience
127 | Apartment Targeting - Blore | vastu-for-penthouse-bangalore | Medium | Pending | Premium segment — top floor vastu rules
128 | Apartment Targeting - Blore | vastu-for-apartment-whitefield | High | Pending | Whitefield apartment buyers — corridor-specific apartment vastu
129 | Apartment Targeting - Blore | vastu-for-apartment-sarjapur-road | High | Pending | Sarjapur Road — dense apartment corridor
130 | Apartment Targeting - Blore | vastu-for-apartment-hebbal | High | Pending | North Bangalore — luxury apartment zone near airport road
131 | Apartment Targeting - Blore | vastu-for-apartment-devanahalli | Medium | Pending | Airport zone — premium villa and apartment buyers
132 | Apartment Targeting - Blore | vastu-for-apartment-kanakapura-road | Medium | Pending | South Bangalore growth corridor
133 | Apartment Targeting - Blore | vastu-for-under-construction-flat | High | Pending | Pre-purchase vastu check — target people buying during construction
134 | Apartment Targeting - Blore | vastu-for-ready-to-move-flat | High | Pending | Ready possession — buyers who cannot modify structure
135 | Apartment Targeting - Blore | vastu-for-resale-apartment | Medium | Pending | Resale buyers — check existing defects before purchase
136 | Apartment Targeting - Blore | vastu-consultation-before-buying-flat | High | Pending | Transactional intent page — 'should I check vastu before buying'
Apartment Targeting - Cities
137 | Apartment Targeting - Cities | vastu-for-apartments-mumbai | High | Pending | BKC, Worli, Powai, Thane — Category A apartment vastu
138 | Apartment Targeting - Cities | vastu-for-apartments-delhi-ncr | High | Pending | Gurgaon sectors, Noida, Greater Noida — high-rise vastu
139 | Apartment Targeting - Cities | vastu-for-apartments-hyderabad | High | Pending | Hitech City, Gachibowli, Kondapur, Banjara Hills
140 | Apartment Targeting - Cities | vastu-for-apartments-chennai | High | Pending | OMR, ECR, Velachery, Anna Nagar
141 | Apartment Targeting - Cities | vastu-for-apartments-pune | High | Pending | Hinjewadi, Kharadi, Wakad, Baner
142 | Apartment Targeting - Cities | vastu-for-apartments-ahmedabad | Medium | Pending | SG Highway corridor — premium apartments
143 | Apartment Targeting - Cities | vastu-for-apartments-kolkata | Medium | Pending | New Town Rajarhat, EM Bypass
144 | Apartment Targeting - Cities | vastu-for-2bhk-apartment-india | High | Pending | National-level 2BHK page — broadest reach
145 | Apartment Targeting - Cities | vastu-for-3bhk-apartment-india | High | Pending | National-level 3BHK page
146 | Apartment Targeting - Cities | vastu-for-apartment-purchase-checklist | High | Pending | Pre-purchase vastu checklist — high commercial intent, shareable
Indian Cities (15)
147 | Indian Cities (15) | vastu-consultant-chennai (WP 255) | High | Done
148 | Indian Cities (15) | vastu-consultant-mumbai (WP 263) | High | Done
149 | Indian Cities (15) | vastu-consultant-delhi (WP 258) | High | Done
150 | Indian Cities (15) | vastu-consultant-hyderabad (WP 260) | High | Done
151 | Indian Cities (15) | vastu-consultant-pune (WP 265) | High | Done
152 | Indian Cities (15) | vastu-consultant-ahmedabad (WP 254) | Medium | Done
153 | Indian Cities (15) | vastu-consultant-kolkata (WP 261) | Medium | Done
154 | Indian Cities (15) | vastu-consultant-gurugram (WP 259) | Medium | Done
155 | Indian Cities (15) | vastu-consultant-noida (WP 264) | Medium | Done
156 | Indian Cities (15) | vastu-consultant-coimbatore (WP 256) | Medium | Done
157 | Indian Cities (15) | vastu-consultant-mysuru (WP 262) | Medium | Done
158 | Indian Cities (15) | vastu-consultant-mangaluru (WP 261b) | Medium | Done
159 | Indian Cities (15) | vastu-consultant-kochi (WP 280) | Medium | Done
160 | Indian Cities (15) | vastu-consultant-jaipur (WP 281) | Medium | Done
161 | Indian Cities (15) | vastu-consultant-chandigarh (WP 282) | Low | Done
Industrial Areas - Bangalore
162 | Industrial Areas - Bangalore | vastu-consultant-peenya-industrial-area | High | Pending | Largest industrial estate in Asia — factory and warehouse vastu
163 | Industrial Areas - Bangalore | vastu-consultant-electronic-city-phase-2 | High | Pending | Phase 2 industrial / IT expansion beyond Phase 1
164 | Industrial Areas - Bangalore | vastu-consultant-bommasandra-industrial-area | High | Pending | KIADB industrial area — manufacturing belt
165 | Industrial Areas - Bangalore | vastu-consultant-jigani-industrial-area | High | Pending | South Bangalore KIADB — pharma, garment, manufacturing
166 | Industrial Areas - Bangalore | vastu-consultant-dobbaspet | Medium | Pending | Tumkur Road industrial zone — warehousing, logistics
167 | Industrial Areas - Bangalore | vastu-consultant-bidadi-industrial-area | Medium | Pending | Toyota plant zone — industrial vastu
168 | Industrial Areas - Bangalore | vastu-consultant-hoskote-industrial-area | Medium | Pending | East Bangalore — KIADB Hoskote zone
169 | Industrial Areas - Bangalore | vastu-for-factory | High | Pending | Generic factory vastu page — targets all industrial searchers
170 | Industrial Areas - Bangalore | vastu-for-warehouse | High | Pending | Warehouse/logistics vastu — high commercial intent
171 | Industrial Areas - Bangalore | vastu-for-it-office-bangalore | High | Pending | IT park office vastu — targets Whitefield, Electronic City, Manyata
Industrial Areas - India
172 | Industrial Areas - India | vastu-for-industrial-area | High | Pending | National-level industrial vastu hub page
173 | Industrial Areas - India | vastu-consultant-faridabad-industrial | Medium | Pending | NCR industrial belt
174 | Industrial Areas - India | vastu-consultant-noida-industrial-sector | Medium | Pending | Noida sectors 58-63 industrial
175 | Industrial Areas - India | vastu-consultant-pune-midc | High | Pending | Pune MIDC — Chakan, Pimpri-Chinchwad, Ranjangaon
176 | Industrial Areas - India | vastu-consultant-chennai-industrial-corridor | High | Pending | OMR IT, Sriperumbudur, Oragadam industrial zones
177 | Industrial Areas - India | vastu-consultant-hyderabad-pharma-city | High | Pending | Pharma City — Genome Valley — specialized industrial vastu
178 | Industrial Areas - India | vastu-consultant-surat-industrial | Medium | Pending | Diamond and textile industry hub
179 | Industrial Areas - India | vastu-consultant-rajkot-industrial | Low | Pending | Engineering goods industrial area
180 | Industrial Areas - India | vastu-consultant-coimbatore-industrial | Medium | Pending | Textile capital — Coimbatore industrial vastu
181 | Industrial Areas - India | vastu-for-commercial-office | High | Pending | Commercial office vastu — national reach
182 | Industrial Areas - India | vastu-for-showroom | High | Pending | Retail showroom vastu — high commercial intent
183 | Industrial Areas - India | vastu-for-restaurant | High | Pending | Restaurant vastu — massive search volume
184 | Industrial Areas - India | vastu-for-hotel | Medium | Pending | Hotel vastu — hospitality industry
International (8)
185 | International (8) | vastu-consultant-usa | High | Done | Live
186 | International (8) | vastu-consultant-uk | High | Done | Live
187 | International (8) | vastu-consultant-canada | High | Done | Live
188 | International (8) | vastu-consultant-australia | High | Done | Live
189 | International (8) | vastu-consultant-uae | High | Done | Live
190 | International (8) | vastu-consultant-singapore | Medium | Done | Live
191 | International (8) | vastu-consultant-new-zealand | Low | Done | Live
192 | International (8) | vastu-consultant-germany | Low | Done | Live
Educational Hub
193 | Educational Hub | Rewrite 15 Edu Hub pages from old format to vv-page-hero — then push | Medium | Pending | Files in pages/educational-hub/ — content is good, template needs upgrade
194 | Educational Hub | vastu-shastra-history | Medium | Pending
195 | Educational Hub | vastu-shastra-principles | Medium | Pending
196 | Educational Hub | vastu-five-elements | Medium | Pending
197 | Educational Hub | vastu-16-zones | Medium | Pending
198 | Educational Hub | vastu-for-wealth | High | Pending | High volume — priority rewrite
199 | Educational Hub | vastu-for-health | High | Pending | High volume — priority rewrite
200 | Educational Hub | vastu-for-marriage | High | Pending | High volume
201 | Educational Hub | vastu-for-career | High | Pending
202 | Educational Hub | vastu-remedies | High | Pending
203 | Educational Hub | vastu-dosha | Medium | Pending
204 | Educational Hub | vastu-for-flat | Medium | Pending
205 | Educational Hub | vastu-for-office | Medium | Pending
206 | Educational Hub | vastu-for-plot | Medium | Pending
207 | Educational Hub | vastu-for-new-home | High | Pending
208 | Educational Hub | VIDS-system-explainer — build fresh, showcase unique methodology | High | Pending | Core differentiator page — VIDS is unique to Vardhini Vastu
House Directions
209 | House Directions | Rewrite 10 House Direction pages to vv-page-hero then push to WP | Medium | Pending
210 | House Directions | vastu-for-north-facing-house | High | Pending | Very high search volume
211 | House Directions | vastu-for-south-facing-house | High | Pending | High volume — controversial = high engagement
212 | House Directions | vastu-for-east-facing-house | High | Pending | High volume
213 | House Directions | vastu-for-west-facing-house | Medium | Pending
214 | House Directions | vastu-for-northeast-facing | Medium | Pending
215 | House Directions | vastu-for-northwest-facing | Medium | Pending
216 | House Directions | vastu-for-southeast-facing | Medium | Pending
217 | House Directions | vastu-for-southwest-facing | Medium | Pending | High intent — SW is the most feared direction
218 | House Directions | vastu-for-corner-plot | Medium | Pending | Niche but very high buyer intent
Core Pages
219 | Core Pages | Homepage — full Rank Math 90+ treatment: title, meta, H1, schema, CTA | High | In Progress | Rank Math 90+ fix in progress (user). Schema clean. Person schema added to About.
220 | Core Pages | About / Raghavendra Hebbur — E-E-A-T author page with credentials, photo, LinkedIn | High | Done | Person schema added: credentials, knowsAbout, hasCredential, ProfilePage + BreadcrumbList |  | 16/05/2026
221 | Core Pages | Contact / Consultation booking page with schema, Maps embed, NAP | High | Done | ContactPage schema fixed: URL corrected /contact/, ProfessionalService type, founder linked |  | 16/05/2026
222 | Core Pages | Testimonials / Reviews page with Review schema | High | Pending
223 | Core Pages | Services page — VIDS consultation types, process, pricing | High | Done | Services schema fixed: breadcrumb URL corrected /services/, business ID unified, founder linked |  | 16/05/2026
224 | Core Pages | Blog — launch with 4 cornerstone posts | Medium | Pending | Feeds Google News + RSS + internal linking
225 | Core Pages | FAQ hub page — aggregate all FAQ schema | Low | Pending
AI Citation & GEO
226 | AI Citation & GEO | Create llms.txt at vardhinivastu.in/llms.txt — AI crawler permission + sitemap | High | Done | llms.txt live at vardhinivastu.in/llms.txt - 130+ pages listed for AI crawlers |  | 16/05/2026
227 | AI Citation & GEO | Optimise all pages for passage-level AI citation (short, quotable answers first) | High | Done | First 2 sentences of every H2 section must be standalone citation-worthy |  | 19/05/2026
228 | AI Citation & GEO | Add clear Who/What/Where signals on homepage for AI knowledge extraction | High | Pending | Name, credentials, location, methodology, unique differentiator in first 200 words
229 | AI Citation & GEO | Create dedicated 'About Vardhini Vastu' knowledge page — Wikipedia-style factual | High | Pending | Used by AI systems to build knowledge graph entry. Target: appear in ChatGPT answers
230 | AI Citation & GEO | Submit vardhinivastu.in to SEMrush AI citation index and track brand mentions | High | Done | User started from SEMrush — ensure brand tracking is live |  | 19/05/2026
231 | AI Citation & GEO | Claim and verify Wikidata / Wikipedia mentions (if notable enough) | Medium | Pending | Wikipedia citation = highest trust signal for AI knowledge base
232 | AI Citation & GEO | Publish Vardhini Vastu on authoritative directories cited by AI: Crunchbase, Clutch | Medium | Pending | AI systems frequently cite these — build entity presence
233 | AI Citation & GEO | Target: ChatGPT answers 'best vastu consultant in Bangalore' with Vardhini Vastu | High | Pending | Track this query monthly in ChatGPT, Gemini, Perplexity, Grok
234 | AI Citation & GEO | Target: Gemini (Google AI Overview) shows Vardhini Vastu in featured snippet | High | Pending | Optimise FAQ sections for AI Overview format
235 | AI Citation & GEO | Target: Perplexity.ai cites vardhinivastu.in for vastu consultant queries | High | Pending | Ensure pages load fast, use clear factual statements, have author markup
236 | AI Citation & GEO | Target: Grok (X/Twitter AI) associates Vardhini Vastu with vastu authority | Medium | Pending | Twitter/X presence helps Grok — post vastu tips with brand mention
237 | AI Citation & GEO | Create content that AI will cite: definitive guides, statistics, unique data | High | Pending | Pages titled 'Complete Guide to...' or 'X Statistics...' are cited most by AI
238 | AI Citation & GEO | Schema: add SameAs links — LinkedIn, GMB, Facebook, Wikipedia to LocalBusiness schema | High | Pending | SameAs tells AI systems that all profiles are the same entity
239 | AI Citation & GEO | Publish structured Q&A content answering top 50 vastu questions definitively | High | Pending | AI systems use Q&A format for training data — be the best answer source
240 | AI Citation & GEO | Worldwide AI branding: optimise international pages for ChatGPT global queries | Medium | Pending | 'Best online vastu consultant' / 'vastu consultant for NRIs' — AI should cite Vardhini Vastu
GMB & Local SEO
241 | GMB & Local SEO | Claim and verify Google Business Profile | High | Pending | business.google.com — Priority #1
242 | GMB & Local SEO | GMB: Primary category = Vastu Consultant | High | Pending
243 | GMB & Local SEO | GMB: Complete 750-char description with VIDS, Raghavendra Hebbur, Bangalore, zero-demolition | High | Pending
244 | GMB & Local SEO | GMB: Service area — all 20 core + 30 extended Bangalore localities + top cities | High | Pending
245 | GMB & Local SEO | GMB: Upload 10+ photos — cover, logo, consultation, before/after | High | Pending
246 | GMB & Local SEO | GMB: Add all services with descriptions (Residential, Commercial, Online, VIDS) | High | Pending
247 | GMB & Local SEO | GMB: Q&A — pre-populate 10 questions | Medium | Pending
248 | GMB & Local SEO | GMB: Enable messaging + set auto-reply | Medium | Pending
249 | GMB & Local SEO | GMB: Weekly posts — tip, offer, or educational content | Medium | Pending | Ongoing — 1 post/week minimum
250 | GMB & Local SEO | GMB: Get first 10 reviews from past clients | High | Pending | Target: 10+ reviews, 4.8+ stars in 90 days
251 | GMB & Local SEO | GMB: Respond to ALL reviews within 24 hours | High | Pending | Ongoing
252 | GMB & Local SEO | GMB: Add appointment / booking link to contact page | High | Pending
253 | GMB & Local SEO | NAP consistency — identical across website, GMB, all citations | High | Pending | Vardhini Vastu ¦ Bangalore ¦ +91 97391 05574
254 | GMB & Local SEO | Citations Tier 1: Justdial, Sulekha, UrbanClap, IndiaMart, NoBroker | High | Pending
255 | GMB & Local SEO | Citations Tier 2: Housing.com, Magicbricks, 99acres vastu section | Medium | Pending
256 | GMB & Local SEO | LocalBusiness schema on homepage and contact page | High | Pending | Already in locality/room pages — add to core pages
257 | GMB & Local SEO | Bing Places listing — import from GMB | Low | Pending
258 | GMB & Local SEO | Apple Maps listing | Low | Pending | mapsconnect.apple.com
Map Rank Tracker
259 | Map Rank Tracker | Set up geo-grid rank tracking for 'vastu consultant bangalore' in Google Maps | High | Pending | Use DataForSEO or BrightLocal geo-grid — track 7x7 grid across Bangalore
260 | Map Rank Tracker | Baseline map rank: record current position for top 10 target search terms | High | Pending | Before GMB optimisation — get baseline, then track weekly
261 | Map Rank Tracker | Target rank: Top 3 in Google Maps Local Pack for 'vastu consultant bangalore' | High | Pending | Primary goal — map pack appearance = direct calls
262 | Map Rank Tracker | Target rank: Appear in map pack for 20 Bangalore locality searches | High | Pending | e.g., 'vastu consultant whitefield' map pack
263 | Map Rank Tracker | Track map ranking for 'vastu consultant [city]' in all 15 Indian cities | Medium | Pending | Secondary cities — monthly tracking
264 | Map Rank Tracker | Optimise GMB reviews for map rank — reviews are #2 local ranking factor | High | Pending | More reviews + higher rating = higher map pack position
265 | Map Rank Tracker | GMB post frequency — weekly posts boost map rank algorithm | Medium | Pending
266 | Map Rank Tracker | Check competitors in map pack monthly — monitor their GMB activity | Medium | Pending
Google News & RSS
267 | Google News & RSS | Enable RSS feed — verify vardhinivastu.in/feed/ is live and valid | High | Pending | WordPress auto-generates RSS — verify it is accessible
268 | Google News & RSS | Submit RSS feed to Google via GSC News Sitemap | High | Pending | GSC > Sitemaps > Add news sitemap URL
269 | Google News & RSS | Apply for Google News publisher inclusion | High | Pending | news.google.com/publications — need consistent publishing schedule first
270 | Google News & RSS | Set up news sitemap: /news-sitemap.xml via Rank Math News Sitemap | High | Pending | Rank Math supports news sitemaps — enable and configure
271 | Google News & RSS | Publish blog content in news-eligible format — dateline, author, category | High | Pending | Google News requires byline, publication date, news category
272 | Google News & RSS | Content calendar: 2 news-eligible posts per week minimum | High | Pending | Topics: vastu for new construction, seasonal vastu tips, VIDS case studies
273 | Google News & RSS | Submit RSS to Feedly, Flipboard, and Indian news aggregators | Medium | Pending | Distribution amplifies each post beyond Google alone
274 | Google News & RSS | Pinterest RSS integration — vastu tips auto-post from RSS | Low | Pending
275 | Google News & RSS | Ensure blog posts include strong keywords in title for Google News ranking | High | Pending | Google News titles must be specific, factual, keyword-rich
Off-Page & Backlinks
276 | Off-Page & Backlinks | Guest article on housing.com / 99acres / Magicbricks blog | High | Pending | Target: 1 guest post/month, link back to vardhinivastu.in
277 | Off-Page & Backlinks | Get listed in Vastu / Astrology expert directories (Astroyogi, Ganeshaspeaks) | Medium | Pending
278 | Off-Page & Backlinks | LinkedIn — Raghavendra Hebbur profile optimised with all credentials | High | Pending | E-E-A-T author signal — links back to site
279 | Off-Page & Backlinks | YouTube channel — 2 vastu tip videos/month, embed on pages | Medium | Pending
280 | Off-Page & Backlinks | PR / media coverage — approach home decor and lifestyle journalists | Low | Pending | 1 press mention per quarter
281 | Off-Page & Backlinks | Build backlinks from apartment community forums (Commonfloor, Apnacomplex) | High | Pending | Residents searching for vastu — link in helpful answers
282 | Off-Page & Backlinks | Quora / Reddit vastu answers with links back to relevant pages | High | Pending | Answer 'vastu consultant bangalore' questions — 2 per week
Analytics & Tracking
283 | Analytics & Tracking | Google Search Console — verify site, submit sitemap, monitor Coverage | High | Done | GSC verified. sitemap_index.xml + sitemap.xml submitted 16/05. 206 URLs queued |  | 16/05/2026
284 | Analytics & Tracking | GA4 — verify tracking fires on ALL 68+ pages including standalone HTML | High | Pending | Standalone HTML pages need GA4 script added manually
285 | Analytics & Tracking | Rank Math Analytics — connect to GSC for keyword rank tracking in WP | High | Pending
286 | Analytics & Tracking | Conversion tracking — WhatsApp click, contact form, call click events in GA4 | High | Done | Primary KPI = daily calls |  | 19/05/2026
287 | Analytics & Tracking | Monthly SEO report — rankings, traffic, GMB views, calls, conversions | Medium | Pending | Baseline at 30 days post-GMB setup
288 | Analytics & Tracking | Set up Google Alerts for 'Vardhini Vastu' and 'Raghavendra Hebbur' | Medium | Pending | Brand monitoring — see who is mentioning you
289 | Analytics & Tracking | SEMrush weekly alerts — keyword changes, backlink gains/losses | High | Pending
Daily Conversion Engine
290 | Daily Conversion Engine | WhatsApp Business — set up auto-reply with consultation booking info | High | Done | Every page has +91 97391 05574 — ensure WhatsApp Business is configured |  | 19/05/2026
291 | Daily Conversion Engine | Click-to-call tracking — ensure all phone numbers are tap-to-call on mobile | High | Pending | tel: links on all pages
292 | Daily Conversion Engine | Response time target: reply to all inquiries within 2 hours | High | Pending | Speed of response = conversion rate
293 | Daily Conversion Engine | Calendly or booking link on every page — reduce friction | High | Pending | Every page CTA should link to a direct booking page
294 | Daily Conversion Engine | GMB: Missed call auto-text — enable if available in your region | Medium | Pending
295 | Daily Conversion Engine | Retargeting pixel (Google/Meta) — track visitors, run retargeting ads | Medium | Pending | Visitors who don't convert get retargeted with consultation offer
296 | Daily Conversion Engine | Offer: Free 15-min vastu Q&A call — funnel to paid consultation | High | Pending | Low-friction entry offer increases contact rate
297 | Daily Conversion Engine | Review funnel: after every consultation, send WhatsApp review request | High | Done | Systematise reviews — every happy client = 1 GMB review |  | 19/05/2026
298 | Daily Conversion Engine | Daily check: GSC clicks, GA4 sessions, WhatsApp messages, GMB calls | High | Done | 30-min daily review of key metrics to stay on top of momentum |  | 19/05/2026
299 | Content Expansion | Create 30 content-gap pages (house numerology, safe/locker, office washroom, NE toilet, TV/electronics, dustbin, home gym, bar, theater, wall art, garage, furniture, windows, dressing room, reception, accounts dept, conference room, server room, owners cabin, utility, file room, office pantry, curtains, game room, boiler, production area, pets corner, home office, sustainable homes, aquarium) | High | Done | WP IDs 688–730; all with Rank Math meta + FAQPage schema | May 2026 | 19/05/2026
300 | WhatsApp Automation | Deploy complete WhatsApp automation suite (floating FAB, tooltip, exit-intent popup, mobile sticky bar, 20 smart context messages, scroll trigger, time-based greetings, GA4+FB Pixel tracking) | High | Done | mu-plugin: vv-whatsapp-suite.php v2.0 (16KB) — guaranteed injection via wp_footer | May 2026 | 19/05/2026
301 | AI / GEO Optimization | AI citation blocks (ai-answer-block, expert-insight, quick-answer, key-takeaways) injected on 8 key pages — stealth mode (visually hidden, AI-readable via clip:rect CSS) | High | Done | Stealth CSS via mu-plugin wp_head priority 1 — verified on all 8 pages live | May 2026 | 19/05/2026
302 | AI / GEO Optimization | llms.txt updated — 149 URLs, entity profile (Vardhini Vastu, Raghavendra Hebbur, VIDS, Lecher Antenna), all AI crawlers whitelisted in robots.txt | High | Done | vardhinivastu.in/llms.txt live — GPTBot, ClaudeBot, PerplexityBot, Google-Extended all allowed | May 2026 | 19/05/2026
303 | AI / GEO Optimization | Rank Math scores >70 + FAQPage schemas fixed on all 30 new pages | High | Done | Focus keywords, meta titles, meta descriptions, FAQPage schema set on all new pages | May 2026 | 19/05/2026
304 | Internal Linking | Internal links added to 19 existing pages (marriage, plot-selection, mandir, T-junction, health, NE cut, pooja room, factory, bedroom, living room, wealth, children, kitchen, bathroom, fish tank, office, mirrors, study room, career) | High | Done | Related Reading blocks injected into existing pages | May 2026 | 19/05/2026

## Bangalore Locality Pipeline
Bangalore Locality Pipeline — 50 Localities Total
20 Live + 30 Extended (South/Kanakapura ¦ East/Hoskote ¦ North/Devanahalli ¦ West/Tumkur Road)
# | Slug | Corridor | Status | Notes
1 | vastu-consultant-whitefield | Core — East | Done | WP Live
2 | vastu-consultant-indiranagar | Core — Central | Done | WP Live
3 | vastu-consultant-koramangala | Core — South | Done | WP Live
4 | vastu-consultant-hsr-layout | Core — South | Done | WP Live
5 | vastu-consultant-electronic-city | Core — South | Done | WP Live
6 | vastu-consultant-jp-nagar | Core — South | Done | WP Live
7 | vastu-consultant-jayanagar | Core — South | Done | WP Live
8 | vastu-consultant-bannerghatta-road | Core — South | Done | WP ID 267
9 | vastu-consultant-sarjapur-road | Core — East | Done | WP ID 268
10 | vastu-consultant-marathahalli | Core — East | Done | WP ID 269
11 | vastu-consultant-yelahanka | Core — North | Done | WP ID 270
12 | vastu-consultant-hebbal | Core — North | Done | WP ID 271
13 | vastu-consultant-rajajinagar | Core — West | Done | WP ID 272
14 | vastu-consultant-malleswaram | Core — West | Done | WP ID 273
15 | vastu-consultant-basavanagudi | Core — South | Done | WP ID 274
16 | vastu-consultant-btm-layout | Core — South | Done | WP ID 275
17 | vastu-consultant-banaswadi | Core — East | Done | WP ID 276
18 | vastu-consultant-bellandur | Core — East | Done | WP ID 277
19 | vastu-consultant-kr-puram | Core — East | Done | WP ID 278
20 | vastu-consultant-nagarbhavi | Core — West | Done | WP ID 279
21 | vastu-consultant-banashankari | South / Kanakapura | Pending | Dense residential
22 | vastu-consultant-uttarahalli | South / Kanakapura | Pending
23 | vastu-consultant-kengeri | South / Mysore Road | Pending
24 | vastu-consultant-rajarajeshwari-nagar | South / Mysore Road | Pending | RR Nagar — fast growth
25 | vastu-consultant-gottigere | South / Bannerghatta Rd | Pending
26 | vastu-consultant-hulimavu | South / Bannerghatta Rd | Pending
27 | vastu-consultant-kanakapura-road | South / Kanakapura | Pending | NICE Road corridor
28 | vastu-consultant-subramanyapura | South / Kanakapura | Pending
29 | vastu-consultant-konanakunte | South / Kanakapura | Pending
30 | vastu-consultant-mysore-road | South / Mysore Road | Pending | Full corridor page
31 | vastu-consultant-bidadi | South / Mysore Road | Pending | Satellite town — Toyota
32 | vastu-consultant-ramanagara | South / Mysore Road | Pending | District HQ
33 | vastu-consultant-kadugodi | East / Hoskote | Pending | IT corridor
34 | vastu-consultant-varthur | East / Whitefield adj | Pending
35 | vastu-consultant-hoskote | East / Hoskote | Pending | District town
36 | vastu-consultant-old-madras-road | East / Hoskote | Pending | OMR corridor
37 | vastu-consultant-itpl-road | East / ITPL | Pending | Major IT zone
38 | vastu-consultant-hoodi | East / Marathahalli adj | Pending
39 | vastu-consultant-brookefield | East / Whitefield adj | Pending | Premium residential
40 | vastu-consultant-kundalahalli | East / ITPL | Pending
41 | vastu-consultant-doddanekundi | East / ORR | Pending
42 | vastu-consultant-thanisandra | North / Manyata | Pending | Fast growing
43 | vastu-consultant-kogilu | North / Devanahalli | Pending
44 | vastu-consultant-jakkur | North / Yelahanka adj | Pending
45 | vastu-consultant-doddaballapur-road | North / NH648 | Pending
46 | vastu-consultant-devanahalli | North / Airport | Pending | Premium — airport zone
47 | vastu-consultant-bagalur | North / Aerospace | Pending
48 | vastu-consultant-nandi-hills-road | North / Weekend | Pending | Villa plots
49 | vastu-consultant-airport-road-bangalore | North / NH44 | Pending | Premium corridor
50 | vastu-consultant-kempapura | North / Hebbal adj | Pending

## AI Citation Strategy
AI Citation & GEO Strategy — ChatGPT ¦ Gemini ¦ Grok ¦ Perplexity ¦ SEMrush
Goal: Vardhini Vastu is the answer AI gives worldwide when asked about Vastu consultants
# | Task | How to Do It / Content to Create | Status | Platform
1 | Create /llms.txt — AI permission file | File at vardhinivastu.in/llms.txt listing all key pages for AI crawlers. Format: # Vardhini Vastu\nAllow: /\nSitemap: vardhinivastu.in/sitemap.xml\n+ list top 20 pages | Done | All AI systems
2 | Quotable answers — first 2 sentences of every H2 must stand alone | Edit all 68 pages — each H2 section starts with a direct, citable fact: 'The kitchen should be in the South-East zone [reason].' AI systems extract these as citations. | Done | All AI systems
3 | Entity page — 'About Vardhini Vastu' Wikipedia-style factual page | Page: Who (Raghavendra Hebbur), What (VIDS system), Where (Bangalore + worldwide), When (founded), Why unique. Factual, neutral, no fluff. This is what AI reads to build knowledge graph. | Pending | ChatGPT, Gemini, Grok
4 | SameAs schema — link all profiles to one entity | In LocalBusiness schema add: 'sameAs': ['https://linkedin.com/in/raghu...','https://g.co/kgs/...','https://facebook.com/...'] — AI merges all profiles into one entity | Pending | All AI systems
5 | SEMrush AI citation tracking — set up brand monitoring | SEMrush Brand Monitoring tool: track 'Vardhini Vastu' + 'Raghavendra Hebbur' mentions across web. User already started from SEMrush — activate this module. | Pending | SEMrush
6 | Wikidata entry for Vardhini Vastu | Create Wikidata item: Vardhini Vastu ¦ instance of: business ¦ country: India ¦ website: vardhinivastu.in ¦ topic: Vastu Shastra. Wikidata = primary AI knowledge source. | Pending | All AI — Wikidata
7 | Clutch.co + Crunchbase listing | AI systems cite Clutch for service businesses. Create detailed profile: services, team size, reviews, speciality. Crunchbase: org profile with description. | Pending | ChatGPT, Perplexity
8 | Publish 'Top 50 Vastu Questions' definitive guide | Page targeting: 'vastu for bedroom', 'vastu for kitchen' etc — 50 Q&As, each with a clear 2-sentence answer. AI systems use Q&A format — this page will be cited heavily. | Pending | All AI systems
9 | Gemini / AI Overview optimisation | For each room/locality page: add a clear 40-word definition at top of page. Google AI Overview pulls from the clearest, most concise answer. Target: featured in AI Overview for 'vastu for kitchen' etc. | In Progress | Google Gemini
10 | ChatGPT Plugin / GPT Store presence | Create a GPT or prompt that references Vardhini Vastu. Or ensure vardhinivastu.in is cited in ChatGPT's web browsing results for vastu queries. | Pending | ChatGPT
11 | Grok (X/Twitter AI) — build Twitter/X presence | Post vastu tips 3x/week on X with #vastu #vastutiips #vastuexpert. Grok trains on X data — consistent brand presence on X = Grok brand recognition. | Pending | Grok / X AI
12 | Perplexity.ai — ensure pages load fast and have clear citations | Perplexity prefers pages with: fast load (<2s), clear author, date, source links, and direct answers. Run PageSpeed on key pages and add author + date markup. | Pending | Perplexity
13 | Worldwide AI visibility — online vastu consultant query | Target global ChatGPT/Gemini answers: 'best online vastu consultant India' / 'vastu consultant for NRIs'. Build international pages with clear online consultation offering. | Pending | All AI — Global
14 | Press mentions and news articles about Vardhini Vastu | AI systems weight news mentions heavily. Target: 1 media mention per quarter in a real estate or lifestyle publication. Even a quote in a blog counts. | Pending | All AI systems
15 | Consistent NAP + VIDS terminology in all content | AI builds brand knowledge from repeated consistent signals. Every page should mention: Vardhini Vastu ¦ Raghavendra Hebbur ¦ VIDS system ¦ Bangalore ¦ zero-demolition. Consistency = entity strength. | Pending | All AI systems
| 305 | AI answer blocks deployed (stealth mode) | Content injected with schema.org/Answer itemscope on 8 key pages; clip:rect CSS hides visually, AI crawlers read raw HTML | Done | All AI systems | 19/05/2026
| 306 | AI crawlers whitelisted in robots.txt + llms.txt live | GPTBot, ClaudeBot, PerplexityBot, Google-Extended, CCBot, meta-externalagent, xAI, Bingbot allowed; llms.txt at root | Done | All AI systems | 19/05/2026

## GMB Quick-Start
Google Business Profile — Quick-Start Checklist (Complete in Order)
GMB = #1 local ranking factor for daily calls. Complete ALL steps before touching anything else.
# | Task | What to Write / Do | Status | Done Date
1 | Claim & verify GMB listing | business.google.com → Add business → Verify by postcard or phone call | Pending
2 | Business Name | Vardhini Vastu (no extra keywords — Google penalises keyword-stuffed names) | Pending
3 | Primary Category | Vastu Consultant | Pending
4 | Additional Categories | Feng Shui Consultant ¦ Spiritual Counselor ¦ Home Consultant | Pending
5 | Business Description (750 chars) | Vardhini Vastu offers professional Vastu Shastra consultancy by Raghavendra Hebbur in Bangalore. Specialising in the VIDS system (Vardhini Integrated Direction System) — a 16-zone degree-accurate Vastu analysis with zero-demolition corrections. Services include residential vastu, commercial vastu, plot analysis, and online consultations across India and worldwide. | Pending
6 | Phone Number | +91 97391 05574 (must match website and all citations exactly — NAP consistency) | Pending
7 | Website URL | https://vardhinivastu.in | Pending
8 | Address / Service Area | Full Bangalore address OR hide address + set service area. Add all 50 localities. | Pending
9 | Opening Hours | Mon-Sat 10am-7pm ¦ Sun By Appointment (accurate hours = higher call rate) | Pending
10 | Services — add each | 1) Residential Vastu 2) Commercial Vastu 3) Online Consultation 4) Plot/Land Vastu 5) VIDS Analysis | Pending
11 | Booking / Appointment Link | https://vardhinivastu.in/vastu-consultant-bangalore-contact/ | Pending
12 | Cover Photo | Professional headshot of Raghavendra Hebbur or clean vastu compass image (1332x750px) | Pending
13 | Logo | Vardhini Vastu logo (250x250px minimum, square) | Pending
14 | Work Photos (8-10) | Consultation session, vastu charts, before/after home layouts, compass analysis | Pending
15 | Q&A — pre-populate 10 questions | Add: What is VIDS? / Do you do online vastu? / Areas served? / Cost? / No demolition? | Pending
16 | Enable Messaging | Turn on GMB messaging — mention WhatsApp +91 97391 05574 in auto-reply | Pending
17 | First GMB Post | Post: '5 Signs Your Home Needs a Vastu Check' — link to /vastu-for-bedroom | Pending
18 | Request first 5-10 reviews | WhatsApp past clients: 'Could you leave a quick Google review? [GMB link]' | Pending
19 | Respond to ALL reviews within 24h | Positive: thank + mention VIDS. Negative: acknowledge + offer offline resolution | Pending
20 | Weekly GMB post schedule | Every Monday: vastu tip. Every Thursday: client success or educational. Rotate topics. | Pending

## Content Calendar
Content Calendar — Google News + RSS + Blog + GMB Posts
2 blog posts/week = Google News eligibility. 1 GMB post/week = map rank boost. All feed RSS.
# | Content Type | Title / Topic | Platform | Status | Notes | Publish Date
1 | Blog Post | 5 Vastu Mistakes in Bangalore Apartments That Cost You Peace | Blog + Google News + RSS | Pending | High local intent — link to room pages
2 | GMB Post | Vastu Tip: Why your refrigerator should never be in the NE corner | GMB | Pending | Link to /vastu-for-kitchen
3 | Blog Post | Vastu for 2BHK Apartments: Room-by-Room Guide | Blog + Google News | Pending | Link to bedroom, kitchen, bathroom pages
4 | GMB Post | Client Result: Corrected master bedroom zone — better sleep in 7 days | GMB | Pending | Social proof post
5 | Blog Post | South-Facing House Vastu: Why It Is Not Inauspicious (The Truth) | Blog + Google News | Pending | High volume search — controversial angle = shares
6 | GMB Post | Vastu for home office — Work from home Vastu tips | GMB | Pending | Link to /vastu-for-study-room
7 | Blog Post | VIDS System Explained: How 16-Zone Vastu Analysis Works | Blog + Google News | Pending | Differentiator content — brand building
8 | GMB Post | Now serving all Whitefield and Sarjapur Road apartments — book a consultation | GMB | Pending | Locality targeting
9 | Blog Post | Vastu Before Buying a Flat: 10 Things to Check | Blog + Google News | Pending | Apartment buyer intent — link to apartment pages
10 | GMB Post | Vastu for Pooja Room: NE is the sacred zone for maximum divine grace | GMB | Pending | Link to /vastu-for-pooja-room
11 | Blog Post | Vastu for IT Professionals in Bangalore: Office and Home Alignment | Blog + Google News | Pending | IT corridor targeting
12 | GMB Post | Online Vastu Consultations Available Worldwide — Book via WhatsApp | GMB | Pending | International + online offer
13 | Blog Post | Vastu for Factory and Industrial Spaces: Zone Rules for Productivity | Blog + Google News | Pending | Industrial segment — new revenue stream
14 | GMB Post | Vastu Tip: The one correction that improves sleep immediately | GMB | Pending | Head direction — bedroom page link
15 | Blog Post | Vardhini Vastu Case Study: Zero-Demolition Correction in Whitefield Apartment | Blog + Google News | Pending | E-E-A-T and social proof
16 | Quora Answer | Answered: Best vastu consultant in Bangalore? | Quora + Off-page | Pending | 2 answers/week — link to site
17 | Blog Post | Vastu for Devanahalli and Airport Road Homes: Luxury Zone Guide | Blog + Google News | Pending | New locality targeting
18 | X/Twitter Post | Thread: 7 vastu rules for the bedroom [with images] | X/Twitter + Grok | Pending | 3 posts/week for Grok AI training
19 | Blog Post | Vastu for NRIs: How to Check Vastu of Your India Home Remotely | Blog + Google News | Pending | International + online consultation
20 | GMB Post | Now covering Devanahalli, Airport Road, and Hebbal — call to book | GMB | Pending | Extended north Bangalore locality push

## AI Citation Timeline
Platform | How It Crawls | Re-crawl Frequency | Expected Visibility | Status for vardhinivastu.in | Actions Taken
Google AI Overviews (Gemini) | Googlebot crawls sitemap; AI Overview picks clearest 40-word answer from indexed pages | Pages recrawled within 1–4 weeks after sitemap submission | 4–8 weeks after indexing for query-specific AI Overviews | llms.txt live, sitemap submitted, FAQPage schema on all pages, answer blocks stealth-injected | ✅ llms.txt ✅ FAQPage schema ✅ Sitemap resubmitted ✅ Answer blocks
ChatGPT (OpenAI / GPTBot) | GPTBot crawls the web periodically; training cutoff + live Bing web search for ChatGPT Plus | Training data: every few months. Live web search: real-time (for Plus users) | 2–6 months for training data inclusion; live web search results: immediate once indexed | GPTBot allowed in robots.txt; llms.txt live with 149 URLs; entity blocks in HTML | ✅ robots.txt GPTBot allowed ✅ llms.txt ✅ HTML entity blocks
Perplexity.ai (PerplexityBot) | Crawls in real-time like a search engine; cites pages that load fast and have clear author + date | Near real-time — can cite a page within days of it being indexed | 1–3 weeks once pages are indexed in Google/Bing | PerplexityBot allowed; pages have author (Raghavendra Hebbur) + date markup; fast LiteSpeed hosting | ✅ robots.txt allowed ✅ Author markup ⏳ PageSpeed optimisation pending
Google Gemini (Direct chat) | Uses Google Search index + Knowledge Graph; Wikidata entity signals help | Same as Google crawl cycle: 1–4 weeks for new content | 4–8 weeks; stronger once Wikidata entry + press mentions exist | Schema.org LocalBusiness + FAQPage deployed; SameAs links pending | ✅ Schema deployed ⏳ Wikidata entry (pending) ⏳ SameAs links (pending)
Grok (X / xAI) | Trains on X (Twitter) data + web crawl (xAI bot) | Web crawl: monthly; X data: near real-time | 3–6 months for web training; X posts: 1–2 weeks if trending | xAI bot allowed in robots.txt; X/Twitter presence not yet started | ✅ robots.txt allowed ⏳ X/Twitter posts (pending)
Claude (Anthropic / ClaudeBot) | ClaudeBot crawls the web for training data; uses Bing for live search | Training: every few months. Bing live: real-time for Pro users | 2–6 months for training; Bing-powered: 1–4 weeks once indexed | ClaudeBot allowed in robots.txt; llms.txt live | ✅ robots.txt allowed ✅ llms.txt
Bing Copilot (Microsoft) | Uses Bing index directly; responds with live citations from Bing search | Real-time from Bing index; submit to Bing Webmaster Tools for faster crawl | 1–3 weeks once in Bing index | Bingbot allowed in robots.txt; Bing Webmaster Tools submission pending | ✅ robots.txt Bingbot allowed ⏳ Bing WMT submission (pending)
Meta AI (meta-externalagent) | Meta crawls public web for RAG (retrieval-augmented generation) | Periodic crawl; frequency not disclosed publicly | 3–6 months estimated | meta-externalagent allowed in robots.txt | ✅ robots.txt allowed
SUMMARY: Earliest expected AI visibility |  | Perplexity: 1–3 weeks | Google AI Overviews: 4–8 weeks | ChatGPT training: 2–6 months | Priority action: Submit to Bing WMT + create Wikidata entry