## 📊 Dashboard
Vardhini Vastu — SEO Master Tracker
vardhinivastu.in · Raghavendra Hebbur · Last updated: 15 May 2026
Metric | Count | % of Total | Description
Total Tasks | 147 | 100% | All tasks across all categories
✅ Completed | 74 | 50% | Done — live on site or process complete
⏳ Pending | 73 | 50% | Not yet started
🔄 In Progress | 0 | — | Currently being worked on
Pages Live on WP | 68 | — | Rooms 25 + Localities 20 + Cities 15 + International 8
GMB Tasks | 18 | — | All pending — highest priority local SEO lever
STATUS LEGEND
✅ Done |  | Task complete, page live on site
⏳ Pending |  | Not started — needs to be picked up
🔄 In Progress |  | Currently being worked on
PRIORITY LEGEND
🔴 High |  | Critical for rankings or conversions — do first
🟡 Medium |  | Important optimisation — do within 30 days
🟢 Low |  | Nice to have — backlog item

## ✅ Master Task List
# | Category | Task / Page | Priority | Status | Notes / URL | Target Date | Done Date
🎯 Strategy & Competitors
1 | 🎯 Strategy & Competitors | Identify top 5 Vastu consultant competitors in Bangalore | High | ✅ Done | Competitors: Mystic Space Vastu, VastuPlus, Vastu Devayah Namah, Astro Vastu, local consultants
2 | 🎯 Strategy & Competitors | Map competitor keyword universe (city pages, locality pages, room pages) | High | ✅ Done | Locality + city + room page structure benchmarked against competitors
3 | 🎯 Strategy & Competitors | Define SEO content roadmap: Rooms, Localities, Cities, International, Educational, Directions | High | ✅ Done | Full roadmap built — 68+ pages planned and executed
4 | 🎯 Strategy & Competitors | Rank Math 90+ blueprint: title format, keyword density, H2 rule, image alt, external link | High | ✅ Done | Blueprint documented in memory/feedback_rankmath_blueprint.md
5 | 🎯 Strategy & Competitors | Set focus keywords per page (Rank Math / meta tags) | High | ⏳ Pending | Each page has SEO title + meta desc in HTML comment — needs to be set in Rank Math for all 68 pages
6 | 🎯 Strategy & Competitors | Track rankings for top 20 target keywords monthly | Medium | ⏳ Pending | Use Google Search Console + Rank Math rank tracker
7 | 🎯 Strategy & Competitors | Competitor backlink gap analysis | Medium | ⏳ Pending | Run /seo backlinks on top 3 competitors
🔧 Technical SEO
8 | 🔧 Technical SEO | vv-blank.php custom template (serves standalone HTML without theme wrapper) | High | ✅ Done | /wp-content/themes/astra/vv-blank.php created and verified
9 | 🔧 Technical SEO | WP permalink structure set to /%postname%/ | High | ✅ Done | Clean URL slugs confirmed on all pages
10 | 🔧 Technical SEO | XML sitemap generation & submission to Google Search Console | High | ⏳ Pending | Rank Math auto-generates sitemap — verify it includes all 68+ new pages, then submit in GSC
11 | 🔧 Technical SEO | robots.txt — verify crawl rules, no important pages blocked | High | ⏳ Pending | Check vardhinivastu.in/robots.txt — ensure locality/city/room pages are crawlable
12 | 🔧 Technical SEO | SSL / HTTPS — verify all pages load over HTTPS | High | ⏳ Pending | Check for mixed content warnings
13 | 🔧 Technical SEO | Core Web Vitals (LCP, CLS, INP) — baseline measurement | High | ⏳ Pending | Run PageSpeed Insights on homepage + 3 locality pages
14 | 🔧 Technical SEO | Mobile rendering — all 68 pages render correctly on mobile | High | ⏳ Pending | Test Astra theme wrapper on fragment pages vs standalone pages
15 | 🔧 Technical SEO | Canonical tags — no duplicate content across city/locality variations | Medium | ⏳ Pending | Check Rank Math canonical settings on all pages
16 | 🔧 Technical SEO | Internal linking audit — link locality pages to city pages, room pages to consultation CTA | Medium | ⏳ Pending | Build cross-link structure: rooms → localities → cities → homepage
17 | 🔧 Technical SEO | Image optimisation — WebP conversion + alt text on all pages | Medium | ⏳ Pending | Upload actual images to /wp-content/uploads/ for all page placeholder img tags
18 | 🔧 Technical SEO | 404 error audit — fix any broken internal links | Low | ⏳ Pending | Scan with Screaming Frog or GSC Coverage report after indexing
📄 Residential Rooms
19 | 📄 Residential Rooms | vastu-for-kitchen | High | ✅ Done | vardhinivastu.in/vastu-for-kitchen · WP ID 283
20 | 📄 Residential Rooms | vastu-for-bedroom | High | ✅ Done | vardhinivastu.in/vastu-for-bedroom · WP ID 284
21 | 📄 Residential Rooms | vastu-for-living-room | High | ✅ Done | vardhinivastu.in/vastu-for-living-room · WP ID 285
22 | 📄 Residential Rooms | vastu-for-dining-room | High | ✅ Done | vardhinivastu.in/vastu-for-dining-room · WP ID 286
23 | 📄 Residential Rooms | vastu-for-bathroom | High | ✅ Done | vardhinivastu.in/vastu-for-bathroom · WP ID 287
24 | 📄 Residential Rooms | vastu-for-pooja-room | High | ✅ Done | vardhinivastu.in/vastu-for-pooja-room · WP ID 288
25 | 📄 Residential Rooms | vastu-for-main-entrance | High | ✅ Done | vardhinivastu.in/vastu-for-main-entrance · WP ID 289
26 | 📄 Residential Rooms | vastu-for-study-room | High | ✅ Done | vardhinivastu.in/vastu-for-study-room · WP ID 290
27 | 📄 Residential Rooms | vastu-for-guest-room | Medium | ✅ Done | vardhinivastu.in/vastu-for-guest-room · WP ID 291
28 | 📄 Residential Rooms | vastu-for-childrens-room | High | ✅ Done | vardhinivastu.in/vastu-for-childrens-room · WP ID 292
29 | 📄 Residential Rooms | vastu-for-master-bedroom | High | ✅ Done | vardhinivastu.in/vastu-for-master-bedroom · WP ID 293
30 | 📄 Residential Rooms | vastu-for-mandir-at-home | High | ✅ Done | vardhinivastu.in/vastu-for-mandir-at-home · WP ID 294
31 | 📄 Residential Rooms | vastu-for-balcony | Medium | ✅ Done | vardhinivastu.in/vastu-for-balcony · WP ID 295
32 | 📄 Residential Rooms | vastu-for-mirrors | Medium | ✅ Done | vardhinivastu.in/vastu-for-mirrors · WP ID 296
33 | 📄 Residential Rooms | vastu-for-shoe-rack | Low | ✅ Done | vardhinivastu.in/vastu-for-shoe-rack · WP ID 297
34 | 📄 Residential Rooms | vastu-for-staircase | Medium | ✅ Done | vardhinivastu.in/vastu-for-staircase · WP ID 298
35 | 📄 Residential Rooms | vastu-for-basement | Medium | ✅ Done | vardhinivastu.in/vastu-for-basement · WP ID 299
36 | 📄 Residential Rooms | vastu-for-car-parking | Medium | ✅ Done | vardhinivastu.in/vastu-for-car-parking · WP ID 300
37 | 📄 Residential Rooms | vastu-for-garden | Medium | ✅ Done | vardhinivastu.in/vastu-for-garden · WP ID 301
38 | 📄 Residential Rooms | vastu-for-water-tank | Medium | ✅ Done | vardhinivastu.in/vastu-for-water-tank · WP ID 302
39 | 📄 Residential Rooms | vastu-for-swimming-pool | Low | ✅ Done | vardhinivastu.in/vastu-for-swimming-pool · WP ID 303
40 | 📄 Residential Rooms | vastu-for-septic-tank | Low | ✅ Done | vardhinivastu.in/vastu-for-septic-tank · WP ID 304
41 | 📄 Residential Rooms | vastu-for-wall-clock | Low | ✅ Done | vardhinivastu.in/vastu-for-wall-clock · WP ID 305
42 | 📄 Residential Rooms | vastu-for-colors | High | ✅ Done | vardhinivastu.in/vastu-for-colors · WP ID 306
43 | 📄 Residential Rooms | vastu-for-toilet | Medium | ✅ Done | vardhinivastu.in/vastu-for-toilet · WP ID 307
📍 Bangalore Localities
44 | 📍 Bangalore Localities | vastu-consultant-whitefield | High | ✅ Done | WP live — standalone HTML via vv-blank
45 | 📍 Bangalore Localities | vastu-consultant-indiranagar | High | ✅ Done | WP live — standalone HTML via vv-blank
46 | 📍 Bangalore Localities | vastu-consultant-koramangala | High | ✅ Done | WP live — standalone HTML via vv-blank
47 | 📍 Bangalore Localities | vastu-consultant-hsr-layout | High | ✅ Done | WP live — standalone HTML via vv-blank
48 | 📍 Bangalore Localities | vastu-consultant-electronic-city | High | ✅ Done | WP live — standalone HTML via vv-blank
49 | 📍 Bangalore Localities | vastu-consultant-jp-nagar | High | ✅ Done | WP live — standalone HTML via vv-blank
50 | 📍 Bangalore Localities | vastu-consultant-jayanagar | High | ✅ Done | WP live — standalone HTML via vv-blank
51 | 📍 Bangalore Localities | vastu-consultant-bannerghatta-road | Medium | ✅ Done | WP ID 267
52 | 📍 Bangalore Localities | vastu-consultant-sarjapur-road | Medium | ✅ Done | WP ID 268
53 | 📍 Bangalore Localities | vastu-consultant-marathahalli | Medium | ✅ Done | WP ID 269
54 | 📍 Bangalore Localities | vastu-consultant-yelahanka | Medium | ✅ Done | WP ID 270
55 | 📍 Bangalore Localities | vastu-consultant-hebbal | Medium | ✅ Done | WP ID 271
56 | 📍 Bangalore Localities | vastu-consultant-rajajinagar | Medium | ✅ Done | WP ID 272
57 | 📍 Bangalore Localities | vastu-consultant-malleswaram | Medium | ✅ Done | WP ID 273
58 | 📍 Bangalore Localities | vastu-consultant-basavanagudi | Medium | ✅ Done | WP ID 274
59 | 📍 Bangalore Localities | vastu-consultant-btm-layout | Medium | ✅ Done | WP ID 275
60 | 📍 Bangalore Localities | vastu-consultant-banaswadi | Low | ✅ Done | WP ID 276
61 | 📍 Bangalore Localities | vastu-consultant-bellandur | Medium | ✅ Done | WP ID 277
62 | 📍 Bangalore Localities | vastu-consultant-kr-puram | Low | ✅ Done | WP ID 278
63 | 📍 Bangalore Localities | vastu-consultant-nagarbhavi | Low | ✅ Done | WP ID 279
🏙️ Indian Cities
64 | 🏙️ Indian Cities | vastu-consultant-chennai | High | ✅ Done | WP ID 255
65 | 🏙️ Indian Cities | vastu-consultant-mumbai | High | ✅ Done | WP ID 263
66 | 🏙️ Indian Cities | vastu-consultant-delhi | High | ✅ Done | WP ID 258
67 | 🏙️ Indian Cities | vastu-consultant-hyderabad | High | ✅ Done | WP ID 260
68 | 🏙️ Indian Cities | vastu-consultant-pune | High | ✅ Done | WP ID 265
69 | 🏙️ Indian Cities | vastu-consultant-ahmedabad | Medium | ✅ Done | WP ID 254
70 | 🏙️ Indian Cities | vastu-consultant-kolkata | Medium | ✅ Done | WP ID 261
71 | 🏙️ Indian Cities | vastu-consultant-gurugram | Medium | ✅ Done | WP ID 259
72 | 🏙️ Indian Cities | vastu-consultant-noida | Medium | ✅ Done | WP ID 264
73 | 🏙️ Indian Cities | vastu-consultant-coimbatore | Medium | ✅ Done | WP ID 256
74 | 🏙️ Indian Cities | vastu-consultant-mysuru | Medium | ✅ Done | WP ID 262
75 | 🏙️ Indian Cities | vastu-consultant-mangaluru | Medium | ✅ Done | WP ID 261 area
76 | 🏙️ Indian Cities | vastu-consultant-kochi | Medium | ✅ Done | WP ID 280
77 | 🏙️ Indian Cities | vastu-consultant-jaipur | Medium | ✅ Done | WP ID 281
78 | 🏙️ Indian Cities | vastu-consultant-chandigarh | Low | ✅ Done | WP ID 282
🌍 International
79 | 🌍 International | vastu-consultant-usa | High | ✅ Done | WP live — standalone HTML via vv-blank
80 | 🌍 International | vastu-consultant-uk | High | ✅ Done | WP live — standalone HTML via vv-blank
81 | 🌍 International | vastu-consultant-canada | High | ✅ Done | WP live — standalone HTML via vv-blank
82 | 🌍 International | vastu-consultant-australia | High | ✅ Done | WP live — standalone HTML via vv-blank
83 | 🌍 International | vastu-consultant-uae | High | ✅ Done | WP live — standalone HTML via vv-blank
84 | 🌍 International | vastu-consultant-singapore | Medium | ✅ Done | WP live — standalone HTML via vv-blank
85 | 🌍 International | vastu-consultant-new-zealand | Low | ✅ Done | WP live — standalone HTML via vv-blank
86 | 🌍 International | vastu-consultant-germany | Low | ✅ Done | WP live — standalone HTML via vv-blank
📚 Educational Hub
87 | 📚 Educational Hub | Rewrite 15 Educational Hub pages from old <article class='vastu-page'> format to new vv-page-hero format | Medium | ⏳ Pending | Files exist locally in pages/educational-hub/ — content good, template needs upgrading
88 | 📚 Educational Hub | vastu-shastra-history | Medium | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
89 | 📚 Educational Hub | vastu-shastra-principles | Medium | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
90 | 📚 Educational Hub | vastu-five-elements | Medium | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
91 | 📚 Educational Hub | vastu-16-zones | Medium | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
92 | 📚 Educational Hub | vastu-for-wealth | High | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
93 | 📚 Educational Hub | vastu-for-health | High | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
94 | 📚 Educational Hub | vastu-for-marriage | High | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
95 | 📚 Educational Hub | vastu-for-career | High | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
96 | 📚 Educational Hub | vastu-remedies | High | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
97 | 📚 Educational Hub | vastu-dosha | Medium | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
98 | 📚 Educational Hub | vastu-for-flat | Medium | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
99 | 📚 Educational Hub | vastu-for-office | Medium | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
100 | 📚 Educational Hub | vastu-for-plot | Medium | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
101 | 📚 Educational Hub | vastu-for-new-home | High | ⏳ Pending | Needs rewrite to vv-page-hero format then push to WP
102 | 📚 Educational Hub | vids-system-explainer | High | ⏳ Pending | VIDS™ unique selling page — needs to be built fresh
🧭 House Directions
103 | 🧭 House Directions | Rewrite 10 House Direction pages from old format to vv-page-hero then push to WP | Medium | ⏳ Pending | Covers: North-facing, South-facing, East-facing, West-facing, NE, NW, SE, SW + corner plots
104 | 🧭 House Directions | vastu-for-north-facing-house | High | ⏳ Pending | High search volume — priority rewrite
105 | 🧭 House Directions | vastu-for-south-facing-house | High | ⏳ Pending | High search volume (controversial topic — good for SEO)
106 | 🧭 House Directions | vastu-for-east-facing-house | High | ⏳ Pending | High search volume
107 | 🧭 House Directions | vastu-for-west-facing-house | Medium | ⏳ Pending
108 | 🧭 House Directions | vastu-for-northeast-facing | Medium | ⏳ Pending
109 | 🧭 House Directions | vastu-for-northwest-facing | Medium | ⏳ Pending
110 | 🧭 House Directions | vastu-for-southeast-facing | Medium | ⏳ Pending
111 | 🧭 House Directions | vastu-for-southwest-facing | Medium | ⏳ Pending | SW is the most feared — high search intent
112 | 🧭 House Directions | vastu-for-corner-plot | Medium | ⏳ Pending | Corner plot vastu — niche but high intent
📝 Core Pages
113 | 📝 Core Pages | Homepage — SEO-optimise title, meta, H1, above-fold content, schema | High | ⏳ Pending | Homepage is the primary landing page — needs full Rank Math 90+ treatment
114 | 📝 Core Pages | About / Raghavendra Hebbur — E-E-A-T author page with credentials, photo, LinkedIn | High | ⏳ Pending | Crucial for E-E-A-T — named expert signals boost all page rankings
115 | 📝 Core Pages | Contact / Consultation booking page | High | ⏳ Pending | Needs optimised CTA, schema, Google Maps embed, NAP
116 | 📝 Core Pages | Testimonials / Reviews page | High | ⏳ Pending | Aggregate reviews with Review schema markup
117 | 📝 Core Pages | Services overview page (what is included in a VIDS™ consultation) | High | ⏳ Pending | Service schema + pricing info page
118 | 📝 Core Pages | Blog — launch with 4 cornerstone posts targeting informational queries | Medium | ⏳ Pending | Topic ideas: vastu mistakes, vastu vs feng shui, vastu for 2024, apartment vastu
119 | 📝 Core Pages | FAQ hub page — aggregate all FAQ schema in one place | Low | ⏳ Pending | Useful for AI Overviews / featured snippets
📌 GMB & Local SEO
120 | 📌 GMB & Local SEO | Claim / verify Google Business Profile (GMB) | High | ⏳ Pending | Business name: Vardhini Vastu — verify at business.google.com
121 | 📌 GMB & Local SEO | GMB: Set primary category = 'Vastu Consultant' | High | ⏳ Pending | Primary: Vastu Consultant; Secondary: Feng Shui Consultant, Spiritual Counselor
122 | 📌 GMB & Local SEO | GMB: Complete business description (750 chars max) with focus keywords | High | ⏳ Pending | Include: VIDS™, Raghavendra Hebbur, Bangalore, zero-demolition, 16-zone analysis
123 | 📌 GMB & Local SEO | GMB: Add service area — cover all 20 Bangalore localities + Tier-1 cities | High | ⏳ Pending | Add each locality as a service area in GMB settings
124 | 📌 GMB & Local SEO | GMB: Upload minimum 10 high-quality photos (exterior, consultation, before/after) | High | ⏳ Pending | Cover photo, logo, team photo, work samples
125 | 📌 GMB & Local SEO | GMB: Add all services with descriptions and prices (consultation types) | High | ⏳ Pending | Residential, Commercial, Plot analysis, Online consultation
126 | 📌 GMB & Local SEO | GMB: Add Q&A — pre-populate with 10 common vastu questions | Medium | ⏳ Pending | Questions should match FAQ content on pages
127 | 📌 GMB & Local SEO | GMB: Enable messaging + set auto-reply | Medium | ⏳ Pending | WhatsApp is primary — also enable GMB messaging
128 | 📌 GMB & Local SEO | GMB: Set up weekly GMB posts (tip, offer, or event) | Medium | ⏳ Pending | 1 post/week minimum — repurpose room/direction page content
129 | 📌 GMB & Local SEO | GMB: Google Reviews — get first 10 reviews from past clients | High | ⏳ Pending | Target: 10+ reviews, 4.8+ rating in first 90 days
130 | 📌 GMB & Local SEO | GMB: Respond to ALL reviews within 24 hours | High | ⏳ Pending | Ongoing — positive and negative both need responses
131 | 📌 GMB & Local SEO | GMB: Add booking link / appointment URL | High | ⏳ Pending | Link to /vastu-consultant-bangalore-contact/
132 | 📌 GMB & Local SEO | NAP consistency — Name, Address, Phone identical across website, GMB, citations | High | ⏳ Pending | NAP: Vardhini Vastu ¦ Bangalore, Karnataka ¦ +91 97391 05574
133 | 📌 GMB & Local SEO | Citation building — Tier 1: Justdial, Sulekha, IndiaMart, UrbanClap | High | ⏳ Pending | Submit to Justdial, Sulekha, UrbanClap/Urban Company, NoBroker, 99acres
134 | 📌 GMB & Local SEO | Citation building — Tier 2: local Bangalore directories, housing.com, magicbricks | Medium | ⏳ Pending | Housing.com consultant directory, Magicbricks vastu section
135 | 📌 GMB & Local SEO | LocalBusiness schema on homepage and contact page | High | ⏳ Pending | Already in room/locality pages — add to homepage and contact page too
136 | 📌 GMB & Local SEO | Bing Places listing (mirrors GMB — quick win) | Low | ⏳ Pending | Import from GMB at bingplaces.com
137 | 📌 GMB & Local SEO | Apple Maps listing (growing in India with iPhone adoption) | Low | ⏳ Pending | Register at mapsconnect.apple.com
🔗 Off-Page & Authority
138 | 🔗 Off-Page & Authority | Get listed in Vastu/Astrology expert directories (Astroyogi, Ganeshaspeaks) | Medium | ⏳ Pending
139 | 🔗 Off-Page & Authority | Guest article on housing/real estate blog (housing.com, 99acres, magicbricks blog) | High | ⏳ Pending | Target: 1 guest post/month with link back to vardhinivastu.in
140 | 🔗 Off-Page & Authority | YouTube channel — 2 short-form vastu tip videos/month | Medium | ⏳ Pending | Short explainer videos rank well for vastu queries — embed on pages
141 | 🔗 Off-Page & Authority | LinkedIn presence — Raghavendra Hebbur profile optimised | High | ⏳ Pending | Author credibility signal for E-E-A-T
142 | 🔗 Off-Page & Authority | PR / media coverage — approach home décor / lifestyle journalists | Low | ⏳ Pending | Target: 1 press mention/quarter in a home/lifestyle publication
📊 Analytics
143 | 📊 Analytics | Google Search Console — verify site, submit sitemap, monitor Coverage | High | ⏳ Pending | Submit sitemap.xml — monitor for crawl errors on all 68+ new pages
144 | 📊 Analytics | Google Analytics 4 — verify tracking on all pages | High | ⏳ Pending | Check GA4 realtime when a page is visited — confirm event firing
145 | 📊 Analytics | Rank Math Analytics — connect GSC to Rank Math dashboard | High | ⏳ Pending | Enables keyword rank tracking inside WP admin
146 | 📊 Analytics | Set up conversion tracking — WhatsApp click, contact form submission, call click | High | ⏳ Pending | GA4 events for all 3 CTA types on all pages
147 | 📊 Analytics | Monthly SEO report — rankings, traffic, GMB views, calls | Medium | ⏳ Pending | Baseline report at 30 days, then monthly

## 📌 GMB Quick-Start
Google Business Profile (GMB) — Quick-Start Checklist
Complete in this order — GMB is the #1 local ranking lever for Vastu consultants in Bangalore
# | Task | What to Write / Do | Status | Done Date
1 | Claim & verify GMB listing | Go to business.google.com → Add your business → Verify by postcard or phone | ⏳ Pending
2 | Business Name | Vardhini Vastu (exactly — no extra keywords) | ⏳ Pending
3 | Primary Category | Vastu Consultant | ⏳ Pending
4 | Additional Categories | Feng Shui Consultant ¦ Spiritual Counselor ¦ Home Consultant | ⏳ Pending
5 | Business Description (750 chars) | Vardhini Vastu offers professional Vastu Shastra consultancy by Raghavendra Hebbur in Bangalore. Specialising in the VIDS™ (Vardhini Integrated Direction System) — a 16-zone, degree-accurate Vastu analysis with zero-demolition corrections. Services: residential vastu, commercial vastu, plot analysis, and online consultations across India and worldwide. | ⏳ Pending
6 | Phone Number | +91 97391 05574 (must match website and citations exactly) | ⏳ Pending
7 | Website URL | https://vardhinivastu.in | ⏳ Pending
8 | Address | Add full Bangalore address (or hide address if home-based + set service area) | ⏳ Pending
9 | Service Area | Add all 20 Bangalore localities + Hyderabad, Chennai, Mumbai, Delhi, Pune (and other cities you serve) | ⏳ Pending
10 | Opening Hours | Mon–Sat 10am–7pm / Sun By Appointment (set accurate hours — affects call rate) | ⏳ Pending
11 | Services — add each with description | 1) Residential Vastu Consultation 2) Commercial Vastu 3) Online Vastu Consultation 4) Plot/Land Vastu 5) VIDS™ Analysis | ⏳ Pending
12 | Appointment / Booking Link | https://vardhinivastu.in/vastu-consultant-bangalore-contact/ | ⏳ Pending
13 | Upload Cover Photo | Professional photo of Raghavendra Hebbur OR clean vastu compass image (1332×750px) | ⏳ Pending
14 | Upload Logo | Vardhini Vastu logo (250×250px minimum, square crop) | ⏳ Pending
15 | Upload 8–10 Work Photos | Consultation session photos, before/after charts, vastu compass images, home diagrams | ⏳ Pending
16 | Pre-populate Q&A (10 questions) | Add these yourself: 'What is VIDS™?', 'Do you do online vastu?', 'What areas do you serve?', 'How much does a consultation cost?', 'Do you require demolition for corrections?' | ⏳ Pending
17 | Enable Messaging | Turn on GMB messaging — also mention WhatsApp +91 97391 05574 in posts | ⏳ Pending
18 | First GMB Post | Post: '5 Signs Your Home Needs a Vastu Check' — link to /vastu-for-bedroom or homepage | ⏳ Pending
19 | Request first 5 reviews | Send WhatsApp/email to past clients with direct GMB review link | ⏳ Pending
20 | Respond to all reviews within 24h | Ongoing — positive: thank + mention VIDS™. Negative: acknowledge + offer to resolve offline | ⏳ Pending

## 🔑 Rank Math Meta
Rank Math Meta — SEO Title, Meta Description & Focus Keyword per Page
Set these in Rank Math for each page to achieve 90+ score. Status = ✅ once set.
Slug / Page | SEO Title (max 60 chars) | Meta Description (max 155 chars) | Focus Keyword | Status
/vastu-for-kitchen | Vastu for Kitchen: 7 Essential Rules for the Agni Zone | Vastu for kitchen — SE placement, cook facing East, stove position, sink placement, and 7 rules for a healthy, prosperous kitchen energy field. | vastu for kitchen | ⏳ Pending
/vastu-for-bedroom | 7 Essential Vastu for Bedroom Rules ¦ Vardhini Vastu | Vastu for bedroom: SW zone, correct head direction, mirror rules & TV placement. Zero-demolition remedies by Raghavendra Hebbur, Bangalore. | vastu for bedroom | ⏳ Pending
/vastu-for-living-room | 7 Proven Vastu for Living Room Tips ¦ Vardhini Vastu | Vastu for living room: zone placement, sofa direction, TV corner & clutter-free Brahmasthana. Zero-demolition remedies by Raghavendra Hebbur. | vastu for living room | ⏳ Pending
/vastu-for-dining-room | Vastu for Dining Room: Direction, Table & Seating Rules ¦ Vardhini | Vastu for dining room — best direction, dining table shape and placement, seating positions, and remedies for common dining room vastu defects. | vastu for dining room | ⏳ Pending
/vastu-for-bathroom | Vastu for Bathroom: Direction, Placement & Rules ¦ Vardhini Vastu | Vastu for bathroom — NW placement, toilet direction, mirror rules & drain placement. Zero-demolition remedies for bathroom vastu defects. | vastu for bathroom | ⏳ Pending
/vastu-for-pooja-room | Vastu for Pooja Room: Sacred Space Rules ¦ Vardhini Vastu | Vastu for pooja room — NE zone, idol placement, lighting & sacred space rules for maximum divine grace energy in your home mandir. | vastu for pooja room | ⏳ Pending
/vastu-for-main-entrance | Vastu for Main Entrance: Door Direction & Rules ¦ Vardhini Vastu | Vastu for main entrance — best door direction, threshold rules, nameplate, and remedies for inauspicious entrance placements. | vastu for main entrance | ⏳ Pending
/vastu-for-study-room | Vastu for Study Room: Direction, Desk & Focus Rules ¦ Vardhini | Vastu for study room — NE or North zone, East-facing desk, bookshelf placement & rules for concentration, memory and academic success. | vastu for study room | ⏳ Pending
/vastu-for-guest-room | Vastu for Guest Room: Direction & Placement ¦ Vardhini Vastu | Vastu for guest room — NW zone, correct head direction and rules for welcoming guests without disturbing main family energy. | vastu for guest room | ⏳ Pending
/vastu-for-childrens-room | Vastu for Children's Room: Direction, Bed & Study Rules | Vastu for children's room — West zone, study desk direction, bed placement and colour rules for growth, focus and health. | vastu for children's room | ⏳ Pending
/vastu-for-master-bedroom | Vastu for Master Bedroom: SW Zone Rules ¦ Vardhini Vastu | Vastu for master bedroom — SW zone placement, head direction, mirror & TV rules for the head of household's authority and deep rest. | vastu for master bedroom | ⏳ Pending
/vastu-for-mandir-at-home | Vastu for Mandir at Home: Sacred Placement Rules ¦ Vardhini | Vastu for mandir at home — NE zone, idol height, facing direction, light rules and remedies for in-home temple placement. | vastu for mandir at home | ⏳ Pending
/vastu-for-balcony | Vastu for Balcony: Direction & Placement Rules ¦ Vardhini Vastu | Vastu for balcony — North or East balcony rules, plant placement, furniture direction and what to avoid in balcony vastu. | vastu for balcony | ⏳ Pending
/vastu-for-mirrors | Vastu for Mirrors: Placement & Rules ¦ Vardhini Vastu | Vastu for mirrors — which walls are correct, which are defects, and the most dangerous mirror placements in bedroom, living room and dining room. | vastu for mirrors | ⏳ Pending
/vastu-for-shoe-rack | Vastu for Shoe Rack: Placement & Direction Rules ¦ Vardhini Vastu | Vastu for shoe rack — correct zone, direction and placement rules to avoid negative energy entry through footwear storage. | vastu for shoe rack | ⏳ Pending
/vastu-for-staircase | Vastu for Staircase: Direction, Placement & Rules ¦ Vardhini Vastu | Vastu for staircase — South or West zone, clockwise turn rule, under-staircase rules and corrections for inauspiciously placed stairs. | vastu for staircase | ⏳ Pending
/vastu-for-basement | Vastu for Basement: Direction & Usage Rules ¦ Vardhini Vastu | Vastu for basement — NW or North preferred, usage rules, lighting requirements and corrections for basements in inauspicious zones. | vastu for basement | ⏳ Pending
/vastu-for-car-parking | Vastu for Car Parking: Direction & Placement Rules ¦ Vardhini | Vastu for car parking — NW or SE zone, slope rules, gate direction and remedies for parking in inauspicious zones. | vastu for car parking | ⏳ Pending
/vastu-for-garden | Vastu for Garden: Direction, Plants & Layout Rules ¦ Vardhini Vastu | Vastu for garden — North and East for open lawn, heavy trees in SW, water features in NE and plant selection for each zone. | vastu for garden | ⏳ Pending
/vastu-for-water-tank | Vastu for Water Tank: Direction & Placement Rules ¦ Vardhini Vastu | Vastu for water tank — NE for underground, SW for overhead, rules for size, shape and slope to maintain correct water element energy. | vastu for water tank | ⏳ Pending
/vastu-for-swimming-pool | Vastu for Swimming Pool: Direction & Placement ¦ Vardhini Vastu | Vastu for swimming pool — North or East zone, shape rules, and remedies for pools in inauspicious zones. | vastu for swimming pool | ⏳ Pending
/vastu-for-septic-tank | Vastu for Septic Tank: Direction & Placement Rules ¦ Vardhini Vastu | Vastu for septic tank — NW or SW zone rules, distance from NE, and the most critical placement mistakes to avoid. | vastu for septic tank | ⏳ Pending
/vastu-for-wall-clock | Vastu for Wall Clock: Direction & Placement Rules ¦ Vardhini Vastu | Vastu for wall clock — North wall primary, East acceptable, what to avoid and the significance of clock direction in vastu shastra. | vastu for wall clock | ⏳ Pending
/vastu-for-colors | Vastu for Colors: Room-wise Colour Rules ¦ Vardhini Vastu | Vastu for colors — zone-specific colour guide for bedroom, kitchen, living room, study room and entrance. Which colours to use and avoid in each direction. | vastu for colors | ⏳ Pending
/vastu-for-toilet | Vastu for Toilet: Direction & Placement Rules ¦ Vardhini Vastu | Vastu for toilet — NW or West zone, toilet seat direction, door rules and corrections for toilets in inauspicious zones like NE and SW. | vastu for toilet | ⏳ Pending
/vastu-consultant-whitefield | Vastu Consultant in Whitefield Bangalore ¦ Vardhini Vastu | Vastu consultant in Whitefield — VIDS™ residential & commercial vastu by Raghavendra Hebbur. Zero-demolition corrections. Call +91 97391 05574. | vastu consultant in whitefield | ⏳ Pending
/vastu-consultant-indiranagar | Vastu Consultant in Indiranagar Bangalore ¦ Vardhini Vastu | Vastu consultant in Indiranagar — VIDS™ system by Raghavendra Hebbur. Residential & commercial vastu. Zero-demolition corrections. | vastu consultant in indiranagar | ⏳ Pending
/vastu-consultant-koramangala | Vastu Consultant in Koramangala Bangalore ¦ Vardhini Vastu | Vastu consultant in Koramangala — VIDS™ 16-zone analysis, zero-demolition corrections by Raghavendra Hebbur. | vastu consultant in koramangala | ⏳ Pending
/vastu-consultant-mumbai | Vastu Consultant in Mumbai ¦ Vardhini Vastu — Online & In-Person | Vastu consultant in Mumbai — VIDS™ system by Raghavendra Hebbur. Online vastu consultations + in-person visits. Call +91 97391 05574. | vastu consultant in mumbai | ⏳ Pending
/vastu-consultant-delhi | Vastu Consultant in Delhi ¦ Vardhini Vastu — Online & In-Person | Vastu consultant in Delhi — degree-accurate VIDS™ analysis, zero-demolition remedies by Raghavendra Hebbur. Online + in-person. | vastu consultant in delhi | ⏳ Pending
/vastu-consultant-chennai | Vastu Consultant in Chennai ¦ Vardhini Vastu | Vastu consultant in Chennai — VIDS™ system by Raghavendra Hebbur. Online & in-person consultations. Zero-demolition corrections. | vastu consultant in chennai | ⏳ Pending